## Payments
Subcontractor | Contract Value | Paid to Date | Retention | Balance Due | Status
Joe's Excavation | 7800 | 7800 | 0 | 0 | Complete
SolidFoundations | 26950 | 26950 | 0 | 0 | Complete
BuildRight Framing | 35310 | 35310 | 0 | 0 | Complete
Spark Electric | 28400 | 18200 | 2840 | 7360 | In Progress
AquaFlow Plumbing | 31200 | 19800 | 3120 | 8280 | In Progress
TopRoof | 14080 | 14080 | 0 | 0 | Complete
Premier Bricklaying | 42000 | 32000 | 4200 | 5800 | In Progress
ColorPro Painters | 11200 | 0 | 1120 | 10080 | Starting