## Active Subbies
SUBCONTRACTOR REGISTER - PROJECT A
ID | Company Name | Contact | Phone | Email | ABN | License | Insurance Expiry | Contract Value | Status
SUB-001 | BigDig Excavations | Tony M | 0412 345 678 | tony@bigdig.com.au | 51 234 567 890 | EXC-12345 | 2025-06-30 | 12120 | COMPLETE
SUB-002 | Precision Concrete Solutions | James Chen | (02) 5555-1234 | james@precisioncon.com | 22445667889 | 123456C | 2024-12-31 | 49300 | COMPLETE
SUB-003 | FastFrame Carpentry | Tom Williams | 04 1234 5678 | tom@fastframe.com.au | 33 556 778 990 | 234567C | 2025-08-15 | 46500 | IN PROGRESS
SUB-004 | TopRoof Tilers | Sarah Brown | 0423456789 |  | 44 667 889 001 | 345678C | 2025-04-20 | 23650 | IN PROGRESS
SUB-005 | Premier Bricklaying | David Lee | (02) 9876-5432 | david@premierbrick.com | 55778889991 | 456789C | 2025-07-10 | 42500 | COMPLETE
SUB-006 | John's Plumbing Services | Robert Chen | 0434567890 | rob@johnsplumbing.com.au | 66 889 990 112 | PL-234567 | 2025-05-25 | 19150 | IN PROGRESS
SUB-007 | Bright Spark Electrical | David Patterson | 04 2345 6789 | david@brightspark.com | 44223445667 | EL-123456 | 2025-09-30 | 28540 | IN PROGRESS
SUB-008 | AirMaster HVAC | Michael Tang | (02) 8888-1234 |  | 77 990 112 233 | AC-567890 | 2025-03-15 | 12500 | COMPLETE
SUB-009 | Complete Plastering Co | Steve Wilson | 0445678901 | steve@completeplaster.com | 88112233445 | 345678C | 2025-06-01 | 20350 | NOT STARTED
SUB-010 | PremierTile | Lisa Wang | 04 3456 7890 | lisa@premiertile.com.au | 99 223 344 556 | 234567C | 2025-07-20 | 12300 | NOT STARTED
SUB-011 | ColorPro Painting | John Smith | (02) 7777-1111 | john@colorpro.com | 11 334 455 667 | 234567C | 2025-08-10 | 14500 | NOT STARTED
SUB-012 | Green Oasis Landscaping | Emma Green | 0456789012 |  | 22 445 556 778 | LAND-12345 | 2025-05-15 | 6800 | NOT STARTED
SUB-013 | SkyHigh Scaffolding | Peter Brown | 04 5678 9012 | peter@skyhigh.com.au | 33 556 667 889 | SCAF-67890 | 2025-04-30 | 4200 | COMPLETE
SUB-014 | SealTight Waterproofing | Andrew Kim | 0467890123 | andrew@sealtight.com | 44 667 778 990 | 234567C | 2023-12-31 | 2800 | COMPLETE
SUB-015 | StrongSteel Reinforcement | Mark Johnson | (02) 6666-2222 |  | 55 778 889 001 | 345678C | 2025-06-20 | 6000 | COMPLETE

## Payment Schedule
SUBCONTRACTOR PAYMENT SCHEDULE
Payment ID | Subcontractor | Invoice # | Description | Amount | GST | Total | Due Date | Status
PAY-001 | BigDig Excavations | BD-2024-001 | Excavation complete | 11018 | 1102 | 12120 | 2024-08-15 | PAID
PAY-002 | Precision Concrete | PC-2024-045 | Footing pour | 18000 | 1800 | 19800 | 2024-08-20 | PAID
PAY-003 | Precision Concrete | PC-2024-067 | Slab pour | 27545 | 2755 | 30300 | 2024-09-10 | PAID
PAY-004 | FastFrame Carpentry | FC-PC-001 | Progress Claim 1 | 9091 | 909 | 10000 | 2024-09-15 | PAID
PAY-005 | FastFrame Carpentry | FC-PC-002 | Progress Claim 2 | 13636 | 1364 | 15000 | 2024-10-05 | PAID
PAY-006 | TopRoof Tilers | TR-2024-156 | Roof tiling progress | 21500 | 2150 | 23650 | 2024-10-15 | OUTSTANDING
PAY-007 | Premier Bricklaying | PB-INV-089 | Brickwork complete | 38636 | 3864 | 42500 | 2024-09-20 | OVERDUE
PAY-008 | John's Plumbing | JP-PC-001 | Rough-in complete | 8682 | 868 | 9550 | 2024-09-25 | PAID
PAY-009 | John's Plumbing | JP-PC-002 | Second fix | 8682 | 868 | 9550 | 2024-10-20 | OUTSTANDING
PAY-010 | Bright Spark Electrical | BSE-PC-001 | Rough-in | 12300 | 1230 | 13530 | 2024-09-30 | PAID
PAY-011 | Bright Spark Electrical | BSE-PC-002 | Second fix progress | 13727 | 1373 | 15100 | 2024-10-25 | NOT DUE
PAY-012 | AirMaster HVAC | AM-2024-456 | HVAC install complete | 11364 | 1136 | 12500 | 2024-09-15 | PAID
PAY-013 | SkyHigh Scaffolding | SH-2024-789 | Scaffolding hire 4 weeks | 3818 | 382 | 4200 | 2024-09-05 | PAID
PAY-014 | SealTight Waterproofing | ST-2024-234 | Waterproofing | 2545 | 255 | 2800 | 2024-08-30 | PAID
PAY-015 | StrongSteel | SS-2024-567 | Steel fixing | 5455 | 545 | 6000 | 2024-08-25 | PAID

## Contact Log
SUBCONTRACTOR COMMUNICATION LOG
Date | Subcontractor | Contact | Subject | Notes
2024-08-15 | BigDig | Tony | Start date | Confirmed excavation start Mon 19/8
2024-08-25 | Precision Concrete | James | Slab booking | Booked for 5/9 - weather permitting
2024-09-01 | FastFrame | Tom | Timber delivery | Delayed 2 days - supplier issue
2024-09-10 | TopRoof | Sarah | Tile selection | Client to confirm color by Fri
2024-09-15 | Premier Brick | David | Payment query | Chasing payment - URGENT
2024-09-20 | John's Plumbing | Robert | Fixture delivery | Delayed - arriving 25/9