## Daily Log
Date | Weather | Trades On Site | Work Completed | Issues
2024-09-02 | Sunny | Framing | Walls up
2024-09-09 | Windy | Framing | Roof trusses
2024-09-16 | Sunny | Roofer | Roof complete
2024-09-23 | Rain | Electrician | Rough-in started | Material delay
2024-09-30 | Sunny | Plumber | Rough-in