## Budget Summary
PROJECT A - 123 SUNSET BOULEVARD - MASTER BUDGET
Contract Value: $650,000
Category | Description | Budget | Actual Spent | Committed | Forecast | Variance | % Complete | Notes
LAND | Land Purchase | 250000 | 250000 | 0 | 250000 | 0 | 100 | PAID
LAND | Stamp Duty | 20000 | 20000 | 0 | 20000 | 0 | 100
LAND | Legal Fees - Conveyancing | 3500 | 3500 | 0 | 3500 | 0 | 100
LAND | Building Consultant Inspection | 850 | 850 | 0 | 850 | 0 | 100
LAND | Soil Testing & Reports | 2200 | 2200 | 0 | 2200 | 0 | 100
DESIGN | Architectural Plans | 15000 | 15000 | 0 | 15000 | 0 | 100
DESIGN | Structural Engineer | 4500 | 4500 | 0 | 4500 | 0 | 100
DESIGN | Building Surveyor | 3200 | 3200 | 0 | 3200 | 0 | 100
DESIGN | Energy Rating Assessment | 850 | 850 | 0 | 850 | 0 | 100
DESIGN | Development Application | 2800 | 2800 | 0 | 2800 | 0 | 100
DESIGN | Building Permit | 1850 | 1850 | 0 | 1850 | 0 | 100
DESIGN | Section 94 Contributions | 8500 | 8500 | 0 | 8500 | 0 | 100 | Paid to Council
DESIGN | Design Revisions | 2000 | 2740 | 0 | 2740 | -740 | 100 | OVER BUDGET - Client changes
SITE PREP | Site Survey | 1800 | 1800 | 0 | 1800 | 0 | 100
SITE PREP | Demolition Existing Structures | 8500 | 8500 | 0 | 8500 | 0 | 100
SITE PREP | Excavation & Earthworks | 10500 | 10920 | 0 | 10920 | -420 | 100 | Extra excavation needed
SITE PREP | Temporary Fencing | 1200 | 1200 | 0 | 1200 | 0 | 100
SITE PREP | Temporary Power & Water | 2800 | 2800 | 0 | 2800 | 0 | 100
SITE PREP | Site Amenities & Toilet | 1450 | 1450 | 0 | 1450 | 0 | 100
FOUNDATION | Concrete - Footings | 8500 | 8500 | 0 | 8500 | 0 | 100
FOUNDATION | Concrete - Slab | 18200 | 18200 | 0 | 18200 | 0 | 100
FOUNDATION | Steel Reinforcement | 6800 | 6800 | 0 | 6800 | 0 | 100
FOUNDATION | Waterproofing Membrane | 2600 | 3490 | 0 | 3490 | -890 | 100 | Extra waterproofing req'd
FOUNDATION | Pier Holes & Concrete Pumping | 3200 | 3200 | 0 | 3200 | 0 | 100
FOUNDATION | Termite Barrier | 1800 | 1800 | 0 | 1800 | 0 | 100
FOUNDATION | Slab Polishing | 4200 | 4200 | 0 | 4200 | 0 | 100
FOUNDATION | Inspections & Testing | 900 | 900 | 0 | 900 | 0 | 100
FRAME | Timber Frame - Walls | 28500 | 28500 | 0 | 28500 | 0 | 95
FRAME | Roof Trusses | 12000 | 12000 | 0 | 12000 | 0 | 95
FRAME | Sarking & Bracing | 6200 | 6200 | 0 | 6200 | 0 | 95
FRAME | Steel Beams & Lintels | 8400 | 8400 | 0 | 8400 | 0 | 100
FRAME | Structural Inspections | 1200 | 1200 | 0 | 1200 | 0 | 95
FRAME | Scaffolding Hire | 4200 | 4200 | 0 | 4200 | 0 | 90
FRAME | Crane Hire | 1400 | 1400 | 0 | 1400 | 0 | 100
EXTERNAL | Brickwork - Face Brick | 42500 | 42500 | 0 | 42500 | 0 | 100
EXTERNAL | Windows & Doors | 18500 | 18500 | 0 | 18500 | 0 | 100
EXTERNAL | Roof Tiles | 15800 | 15800 | 0 | 15800 | 0 | 95
EXTERNAL | Ridge Capping & Flashing | 2850 | 2850 | 0 | 2850 | 0 | 95
EXTERNAL | Gutters & Downpipes | 1800 | 0 | 1800 | 1800 | 0 | 0 | NOT YET INVOICED
EXTERNAL | External Cladding | 8200 | 0 | 8200 | 8200 | 0 | 0 | Materials on site
EXTERNAL | Garage Door | 2800 | 0 | 2800 | 2800 | 0 | 0 | Ordered
EXTERNAL | External Paint | 6500 | 0 | 0 | 6500 | 0 | 0 | Not started
EXTERNAL | Balustrades | 4200 | 0 | 0 | 4200 | 0 | 0 | Not started
SERVICES | Plumbing - Rough In | 8500 | 8500 | 0 | 8500 | 0 | 100
SERVICES | Plumbing - Fixtures | 6200 | 0 | 6200 | 6780 | -580 | 0 | OVER - Client upgrade
SERVICES | Hot Water System | 2450 | 0 | 2450 | 2450 | 0 | 0 | Ordered
SERVICES | Electrical - Rough In | 12000 | 12000 | 0 | 12000 | 0 | 100
SERVICES | Electrical - Second Fix | 8500 | 0 | 8500 | 9740 | -1240 | 0 | OVER - Extra points
SERVICES | Light Fittings | 4200 | 0 | 0 | 4200 | 0 | 0 | Not selected yet
SERVICES | HVAC System | 12500 | 0 | 12500 | 12500 | 0 | 0 | Ducted AC installed
SERVICES | Solar Panels & Inverter | 8500 | 0 | 0 | 8500 | 0 | 0 | Not started
SERVICES | NBN & Communications | 1200 | 0 | 0 | 1200 | 0 | 0
SERVICES | Security System | 2800 | 0 | 0 | 2800 | 0 | 0
INTERNAL | Plasterboard & Cornice | 20350 | 0 | 20350 | 20350 | 0 | 0 | Booked for Oct
INTERNAL | Internal Painting | 14500 | 0 | 0 | 14500 | 0 | 0 | After plaster
INTERNAL | Kitchen Cabinets | 28000 | 0 | 0 | 30100 | -2100 | 0 | OVER - Client upgrade NOT INVOICED
INTERNAL | Kitchen Benchtops - Stone | 8500 | 0 | 0 | 8500 | 0 | 0
INTERNAL | Bathroom Vanities | 5200 | 0 | 0 | 5200 | 0 | 0
INTERNAL | Tiling - Bathrooms & Kitchen | 12300 | 0 | 0 | 12300 | 0 | 0
INTERNAL | Timber Flooring | 18500 | 0 | 0 | 18500 | 0 | 0
INTERNAL | Carpet | 8200 | 0 | 0 | 8200 | 0 | 0
INTERNAL | Internal Doors & Hardware | 6800 | 0 | 0 | 6800 | 0 | 0
INTERNAL | Wardrobe Fitouts | 9200 | 0 | 0 | 9200 | 0 | 0
INTERNAL | Splashbacks | 2400 | 0 | 0 | 2400 | 0 | 0
INTERNAL | Laundry Fitout | 3200 | 0 | 0 | 3200 | 0 | 0
EXTERNAL WORKS | Driveway - Concrete | 8500 | 0 | 0 | 8500 | 0 | 0
EXTERNAL WORKS | Fencing | 12500 | 0 | 0 | 12500 | 0 | 0
EXTERNAL WORKS | Landscaping | 6800 | 0 | 0 | 6800 | 0 | 0
EXTERNAL WORKS | Retaining Walls | 8200 | 0 | 0 | 8200 | 0 | 0
EXTERNAL WORKS | Letterbox & Entry | 1200 | 0 | 0 | 1200 | 0 | 0
EXTERNAL WORKS | External Lighting | 2400 | 0 | 0 | 2400 | 0 | 0
PROFESSIONAL | Building Insurance | 4200 | 4200 | 0 | 4200 | 0 | 100
PROFESSIONAL | Project Management | 8500 | 6330 | 2170 | 8500 | 0 | 75 | Monthly fees
PROFESSIONAL | Site Supervisor | 12000 | 9000 | 3000 | 12000 | 0 | 75 | Weekly fees
PROFESSIONAL | Council Fees & Inspections | 2800 | 2800 | 0 | 2800 | 0 | 100
TOTAL |  | 650000

## Cost Detail
DETAILED COST TRANSACTIONS
Date | Supplier | Invoice# | Description | Category | Amount | GST | Total | Status
15/01/2024 | Smith Family Trust | INV-1000 | Land Purchase | LAND | 250000 | 25000 | 275000 | OUTSTANDING
22/01/2024 | State Revenue Office | INV-1001 | Stamp Duty | LAND | 20000 | 2000 | 22000 | PAID
29/01/2024 | Johnson & Partners Legal | INV-1002 | Legal Fees | LAND | 3500 | 350 | 3850 | OUTSTANDING
05/02/2024 | Building Check Australia | INV-1003 | Inspection | LAND | 850 | 85 | 935 | PAID
12/02/2024 | Geotech Solutions | INV-1004 | Soil Test | LAND | 2200 | 220 | 2420 | OUTSTANDING
19/02/2024 | Design Studio | INV-1005 | Architect | DESIGN | 15000 | 1500 | 16500 | PAID
26/02/2024 | Structural Solutions | INV-1006 | Engineer | DESIGN | 4500 | 450 | 4950 | PAID
04/03/2024 | ABC Building Surveyors | INV-1007 | Surveyor | DESIGN | 3200 | 320 | 3520 | PAID
11/03/2024 | BigDig Excavations | INV-1008 | Excavation | SITE PREP | 10920 | 1092 | 12012 | PAID
18/03/2024 | ReadyMix Concrete | INV-1009 | Concrete | FOUNDATION | 7872 | 787.2 | 8659.2 | PAID

## Cashflow
WEEKLY CASHFLOW FORECAST
Week Ending | Cash In | Cash Out | Net Cashflow | Running Balance
22/01/2024 | 97500 | 40974 | 56526 | 156526
29/01/2024 | 0 | 24828 | -24828 | 131698
05/02/2024 | 0 | 20319 | -20319 | 111379
12/02/2024 | 0 | 37153 | -37153 | 74226
19/02/2024 | 97500 | 39853 | 57647 | 131873
26/02/2024 | 0 | 25568 | -25568 | 106305
04/03/2024 | 0 | 24378 | -24378 | 81927
11/03/2024 | 0 | 42509 | -42509 | 39418
18/03/2024 | 0 | 26273 | -26273 | 13145
25/03/2024 | 0 | 22968 | -22968 | -9823
01/04/2024 | 0 | 21518 | -21518 | -31341
08/04/2024 | 0 | 18252 | -18252 | -49593
15/04/2024 | 130000 | 43070 | 86930 | 37337
22/04/2024 | 0 | 39688 | -39688 | -2351
29/04/2024 | 0 | 36053 | -36053 | -38404
06/05/2024 | 0 | 25636 | -25636 | -64040
13/05/2024 | 130000 | 43731 | 86269 | 22229
20/05/2024 | 0 | 37535 | -37535 | -15306
27/05/2024 | 0 | 35805 | -35805 | -51111
03/06/2024 | 0 | 43068 | -43068 | -94179

## Notes & Calcs
PROJECT NOTES & CALCULATIONS
BUDGET STATUS:
Original Budget: | $650,000
Current Forecast: | $658,500
Variance: | ($8,500)
MAJOR ISSUES:
1. Kitchen cabinets over by $2,100 - client upgrade NOT invoiced
2. Electrical over by $1,240 - extra power points variation approved
3. Plumbing fixtures over by $580 - client selections
CLIENT VARIATIONS NOT INVOICED:
VO-002: Extra window | $1,200
VO-003: Bathroom tile upgrade | $2,800
VO-004: Extra waterproofing | $1,500
VO-006: 8x power points | $960
TOTAL REVENUE LEAKAGE: | $6,460