## Critical Path
Activity | Duration | Dependencies | Float | Critical?
Foundation | 23 days | Site Prep | 0 days | YES
Frame | 30 days | Foundation | 0 days | YES
Roof | 15 days | Frame | 0 days | YES
External Walls | 40 days | Frame | 5 days | NO
Plumbing Rough-in | 20 days | Frame | 10 days | NO