## Delays
Date | Reason | Days Lost | Impact | Mitigation
2024-08-05 | Heavy Rain | 2 | Foundation delayed | Overtime
2024-09-11 | Wind - Roof | 1 | Roof install stopped | Extra crew
2024-09-23 | Material shortage | 3 | Electrical delayed | Alternative supplier