## Milestones
Milestone | Planned Date | Actual Date | Variance (days) | Status
Slab Down | 2024-08-20 | 2024-08-25 | 5 | Complete
Frame Complete | 2024-09-20 | 2024-09-25 | 5 | Complete
Lockup | 2024-10-25 |  |  | In Progress
Fixing Complete | 2024-11-25 |  |  | Not Started
Practical Completion | 2024-12-15 |  |  | Not Started