## Snagging
Item | Location | Trade | Priority | Status
Paint touch-up required | Living Room | Painter | Low | Open
Door alignment | Bedroom 2 | Carpenter | Medium | Open
Tile crack | Bathroom 1 | Tiler | High | Open
Window seal | Kitchen | Window installer | Medium | Open