## Architectural
Drawing Number | Drawing Title | Revision | Date Issued | Status | Notes
A-DA-101 | FLOOR PLAN - LEVEL 12 - DEMOLITION | A | 2024-07-28 | For Construction
A-DA-102 | FLOOR PLAN - LEVEL 12 - PROPOSED | B | 2024-07-16 | For Review
A-DA-103 | REFLECTED CEILING PLAN | D | 2024-07-22 | For Construction
A-DA-104 | FINISHES PLAN | D | 2024-08-03 | For Construction
A-DA-105 | FURNITURE PLAN | D | 2024-07-25
A-DA-106 | SECTIONS - SHEET 1 | C | 2024-07-13 | For Construction
A-DA-107 | SECTIONS - SHEET 2 | A | 2024-08-07 | For Construction
A-DA-108 | ELEVATIONS - INTERNAL | D | 2024-08-08 | For Information
A-DA-109 | RECEPTION DESK - DETAILS | D | 2024-07-28 | Superseded | Clash with structural beam - check
A-DA-110 | KITCHEN JOINERY - DETAILS | A | 2024-08-06 | Superseded
A-DA-111 | MEETING ROOM 1 & 2 - DETAILS | A | 2024-07-28 | For Construction
A-DA-112 | DOOR & WINDOW SCHEDULE | B | 2024-08-06 | For Review
A-DA-113 | PARTITION TYPES | A | 2024-07-11 | For Construction
A-DA-114 | FLOORING SETOUT | A | 2024-07-13 | For Information
A-DA-115 | BRANDING & SIGNAGE | A | 2024-08-04 | Superseded

## Structural
Drawing Number | Drawing Title | Revision | Date Issued | Status | Drawn By
S-01 | STRUCTURAL NOTES & SPECIFICATIONS | A | 2024-07-20 | For Construction | J.Doe
S-02 | FLOOR PENETRATION DETAILS | B | 2024-07-19 | For Construction | J.Doe
S-03 | SUSPENDED SLAB SUPPORT DETAILS | B | 2024-07-23 | For Construction | A.Smith
S-04 | CEILING SUPPORT FRAMEWORK | B | 2024-07-18 | For Construction | A.Smith
S-05 | SERVER ROOM - SLAB STRENGTHENING | B | 2024-07-22 | For Construction | J.Doe

## MEP
Drawing Number | Drawing Title | Revision | Date Issued | Status
M-01 | MECHANICAL - HVAC LAYOUT | C | 2024-08-01 | For Construction
M-02 | MECHANICAL - DUCTWORK DETAILS | B | 2024-08-06 | For Construction
E-01 | ELECTRICAL - LIGHTING & POWER | D | 2024-08-11 | For Construction
E-02 | ELECTRICAL - COMMS & DATA | C | 2024-08-16 | For Construction
E-03 | ELECTRICAL - SINGLE LINE DIAGRAM | B | 2024-08-21 | For Construction
P-01 | PLUMBING - FITOUT PLAN | A | 2024-08-26 | For Construction
F-01 | FIRE - SPRINKLER & DETECTOR LAYOUT | C | 2024-08-31 | For Construction

## Coordination Notes
Meeting 28/08/2024
- HVAC unit clashes with ceiling grid in Zone 3. Mech consultant to review.
- Final colour for reception desk TBC by client.
OLD INFO: ~~Use 2-hour fire rated plasterboard~~