## Gantt View
ID | Task Name | Duration (Days) | Start Date | Finish Date | Predecessors | Status | Notes
1 | PROJECT START | 0 | 2024-07-15 | 2024-07-15 |  | Complete
2 | Lease Finalized | 5 | 2024-07-16 | 2024-07-20 | 1 | Complete
3 | Design Development | 30 | 2024-07-21 | 2024-08-19 | 2 | Complete
4 | Permit Application | 5 | 2024-08-20 | 2024-08-24 | 3 | Complete
5 | Permit Approval | 20 | 2024-08-25 | 2024-09-13 | 4 | Complete
6 | Subcontractor Tenders | 15 | 2024-08-20 | 2024-09-03 | 3 | Complete
7 | Award Subcontracts | 10 | 2024-09-04 | 2024-09-13 | 6 | Complete
8 | Site Mobilization | 5 | 2024-09-14 | 2024-09-18 | 5,7 | Complete
9 | Demolition | 10 | 2024-09-19 | 2024-09-28 | 8 | In Progress | Asbestos discovery delayed completion by 3 days
10 | Framing & Partitions | 25 | 2024-09-29 | 2024-10-23 | 9 | In Progress
11 | HVAC Rough-in | 15 | 2024-10-24 | 2024-11-07 | 10 | CRITICAL PATH
12 | Electrical Rough-in | 15 | 2024-10-24 | 2024-11-07 | 10 | In Progress
13 | Plumbing Rough-in | 10 | 2024-10-24 | 2024-11-02 | 10 | In Progress
14 | Ceiling Grid Installation | 10 | 2024-11-08 | 2024-11-17 | 11,12,13 | Not Started
15 | Plasterboard & Finishing | 20 | 2024-11-18 | 2024-12-07 | 14 | Not Started
16 | Flooring Preparation | 5 | 2024-12-08 | 2024-12-12 | 15 | Not Started
17 | Painting | 15 | 2024-12-08 | 2024-12-22 | 15 | Not Started
18 | Joinery Installation | 20 | 2024-12-13 | 2025-01-01 | 16 | Not Started
19 | HVAC Fit-off | 10 | 2024-12-23 | 2025-01-01 | 17 | Not Started
20 | Electrical Fit-off | 10 | 2024-12-23 | 2025-01-01 | 17 | Not Started
21 | Plumbing Fit-off | 5 | 2024-12-23 | 2024-12-27 | 17 | Not Started
22 | Flooring Installation | 10 | 2025-01-02 | 2025-01-11 | 18 | Not Started
23 | Final Inspections | 5 | 2025-01-12 | 2025-01-16 | 22 | Not Started
24 | Defects Rectification | 10 | 2025-01-17 | 2025-01-26 | 23 | Not Started
25 | PROJECT COMPLETE | 0 | 2025-01-27 | 2025-01-27 | 24 | Not Started

## Schedule Notes
Schedule Revision Log
Rev A - 15/07/2024 - Baseline schedule
Rev B - 28/07/2024 - Added 3 days to demo due to asbestos
Rev C - 15/08/2024 - Client delay on joinery finish selection (2 day float used)