## PO Register
PURCHASE ORDER REGISTER
[8 empty] | Status | Count
PO# | Date | Supplier | Description | Amount | Delivery Date | Invoice Received | Status | COMPLETE
PO-2024-1000 | 01/07/2024 | Spark Electrical | Electrical materials | 22080 | 12/07/2024 | YES | COMPLETE | PENDING
PO-2024-1001 | 04/07/2024 | Aqua Plumbing | Plumbing supplies | 10764 | 23/07/2024 | YES | COMPLETE | CANCELLED
PO-2024-1002 | 07/07/2024 | BuildMart | General supplies | 20411 | 26/07/2024 | YES | COMPLETE
PO-2024-1003 | 10/07/2024 | Tile Palace | Floor & wall tiles | 1734 | 28/07/2024 | NO | COMPLETE
PO-2024-1004 | 13/07/2024 | Timber Supplies Co | Structural timber | 4189 | 29/07/2024 | YES | COMPLETE
PO-2024-1005 | 16/07/2024 | Aqua Plumbing | Plumbing supplies | 2428 | 01/08/2024 | YES | COMPLETE
PO-2024-1006 | 19/07/2024 | Window World | Windows & doors | 19772 | 31/07/2024 | YES | COMPLETE
PO-2024-1007 | 22/07/2024 | Bob's Hardware | Timber & fixings | 1704 | 04/08/2024 | YES | COMPLETE
PO-2024-1008 | 25/07/2024 | Pacific Paint | Paint & materials | 13698 | 10/08/2024 | NO | DELIVERED
PO-2024-1009 | 28/07/2024 | Tile Palace | Floor & wall tiles | 15887 | 16/08/2024 | YES | COMPLETE
PO-2024-1010 | 31/07/2024 | Tile Palace | Floor & wall tiles | 20001 | 08/08/2024 | NO | COMPLETE
PO-2024-1011 | 03/08/2024 | BuildMart | General supplies | 24854 | 11/08/2024 | YES | PENDING
PO-2024-1012 | 06/08/2024 | Spark Electrical | Electrical materials | 13009 | 25/08/2024 | YES | PENDING
PO-2024-1013 | 09/08/2024 | Pacific Paint | Paint & materials | 16932 | 18/08/2024 | YES | COMPLETE
PO-2024-1014 | 12/08/2024 | Spark Electrical | Electrical materials | 15832 | 26/08/2024 | YES | COMPLETE
PO-2024-1015 | 15/08/2024 | Aqua Plumbing | Plumbing supplies | 10657 | 01/09/2024 | YES | COMPLETE
PO-2024-1016 | 18/08/2024 | Aqua Plumbing | Plumbing supplies | 6971 | 27/08/2024 | YES | COMPLETE
PO-2024-1017 | 21/08/2024 | BuildMart | General supplies | 2665 | 11/09/2024 | YES | COMPLETE
PO-2024-1018 | 24/08/2024 | Window World | Windows & doors | 16256 | 05/09/2024 | YES | COMPLETE
PO-2024-1019 | 27/08/2024 | Window World | Windows & doors | 24671 | 09/09/2024 | YES | COMPLETE
PO-2024-1020 | 30/08/2024 | Timber Supplies Co | Structural timber | 10469 | 10/09/2024 | YES | PENDING
PO-2024-1021 | 02/09/2024 | Spark Electrical | Electrical materials | 4077 | 15/09/2024 | YES | DELIVERED
PO-2024-1022 | 05/09/2024 | Spark Electrical | Electrical materials | 15482 | 16/09/2024 | NO | COMPLETE
PO-2024-1023 | 08/09/2024 | Steel Direct | Steel beams | 2061 | 26/09/2024 | YES | PENDING
PO-2024-1024 | 11/09/2024 | Window World | Windows & doors | 23355 | 27/09/2024 | YES | DELIVERED
PO-2024-1025 | 14/09/2024 | Steel Direct | Steel beams | 15954 | 01/10/2024 | NO | COMPLETE
PO-2024-1026 | 17/09/2024 | BuildMart | General supplies | 8871 | 25/09/2024 | YES | COMPLETE
PO-2024-1027 | 20/09/2024 | Tile Palace | Floor & wall tiles | 13995 | 06/10/2024 | YES | COMPLETE
PO-2024-1028 | 23/09/2024 | BuildMart | General supplies | 11014 | 04/10/2024 | YES | COMPLETE
PO-2024-1031 | 2024-03-30 | Premium Plumbing | Materials and services for construction - Phase 3 | 32545 | 2024-04-19 | NO | CANCELLED
PO-2024-1032 | 2024-06-19 | Ace Carpentry | Materials and services for construction - Phase 2 | 70073 | 2024-06-30 | YES | COMPLETE
PO-2024-1033 | 2024-03-24 | Ace Carpentry | Materials and services for construction - Phase 1 | 38017 | 2024-04-17 | NO | COMPLETE
PO-2024-1034 | 2024-06-15 | Ace Carpentry | Materials and services for construction - Phase 5 | 7977 | 2024-07-09 | YES | COMPLETE
PO-2024-1035 | 2024-03-26 | Concrete Co | Materials and services for construction - Phase 3 | 28882 | 2024-04-13 | YES | COMPLETE
PO-2024-1036 | 2024-07-13 | Steel Supplies | Materials and services for construction - Phase 5 | 78013 | 2024-07-24 | YES | COMPLETE
PO-2024-1037 | 2024-03-30 | Sydney Tiles | Materials and services for construction - Phase 5 | 41158 | 2024-04-26 | YES | CANCELLED
PO-2024-1038 | 2024-02-01 | Timber Traders | Materials and services for construction - Phase 5 | 22389 | 2024-02-25 | YES | COMPLETE
PO-2024-1039 | 2024-07-10 | Ace Carpentry | Materials and services for construction - Phase 2 | 41229 | 2024-07-25 | YES | CANCELLED
PO-2024-1040 | 2024-07-23 | Steel Supplies | Materials and services for construction - Phase 4 | 43844 | 2024-08-11 | YES | COMPLETE
PO-2024-1041 | 2024-05-17 | Concrete Co | Materials and services for construction - Phase 3 | 12070 | 2024-06-10 | YES | PENDING
PO-2024-1042 | 2024-04-07 | Premium Plumbing | Materials and services for construction - Phase 3 | 77877 | 2024-04-30 | YES | COMPLETE
PO-2024-1043 | 2024-07-25 | BuildMart | Materials and services for construction - Phase 2 | 66761 | 2024-08-23 | YES | COMPLETE
PO-2024-1044 | 2024-02-21 | Ace Carpentry | Materials and services for construction - Phase 5 | 24010 | 2024-03-04 | NO | COMPLETE
PO-2024-1045 | 2024-07-28 | Premium Plumbing | Materials and services for construction - Phase 1 | 20404 | 2024-08-08 | YES | PENDING
PO-2024-1046 | 2024-02-22 | Steel Supplies | Materials and services for construction - Phase 5 | 8321 | 2024-03-18 | NO | COMPLETE
PO-2024-1047 | 2024-05-25 | BuildMart | Materials and services for construction - Phase 2 | 25097 | 2024-06-16 | YES | COMPLETE
PO-2024-1048 | 2024-06-01 | Premium Plumbing | Materials and services for construction - Phase 2 | 41098 | 2024-06-09 | NO | CANCELLED
PO-2024-1049 | 2024-02-01 | Timber Traders | Materials and services for construction - Phase 1 | 30674 | 2024-02-23 | YES | PENDING
PO-2024-1050 | 2024-04-27 | Sydney Tiles | Materials and services for construction - Phase 5 | 29022 | 2024-05-17 | YES | PENDING
PO-2024-1051 | 2024-04-05 | Steel Supplies | Materials and services for construction - Phase 5 | 72965 | 2024-05-02 | NO | COMPLETE
PO-2024-1052 | 2024-05-27 | Timber Traders | Materials and services for construction - Phase 3 | 21477 | 2024-06-21 | YES | COMPLETE
PO-2024-1053 | 2024-04-05 | Ace Carpentry | Materials and services for construction - Phase 3 | 67543 | 2024-04-27 | NO | COMPLETE
PO-2024-1054 | 2024-03-26 | Ace Carpentry | Materials and services for construction - Phase 5 | 34808 | 2024-04-07 | NO | COMPLETE
PO-2024-1055 | 2024-02-22 | Concrete Co | Materials and services for construction - Phase 5 | 70536 | 2024-03-12 | YES | COMPLETE
PO-2024-1056 | 2024-04-04 | Pro Paint | Materials and services for construction - Phase 4 | 7066 | 2024-04-29 | YES | PENDING
PO-2024-1057 | 2024-01-20 | Ace Carpentry | Materials and services for construction - Phase 1 | 43711 | 2024-02-16 | YES | CANCELLED
PO-2024-1058 | 2024-07-26 | Ace Carpentry | Materials and services for construction - Phase 4 | 14145 | 2024-08-02 | YES | CANCELLED
PO-2024-1059 | 2024-05-21 | BuildMart | Materials and services for construction - Phase 3 | 17143 | 2024-06-18 | NO | CANCELLED
PO-2024-1060 | 2024-05-06 | Premium Plumbing | Materials and services for construction - Phase 3 | 63837 | 2024-05-31 | NO | COMPLETE
PO-2024-1061 | 2024-03-24 | Sydney Tiles | Materials and services for construction - Phase 4 | 32706 | 2024-04-18 | YES | COMPLETE
PO-2024-1062 | 2024-03-01 | Concrete Co | Materials and services for construction - Phase 2 | 55242 | 2024-03-27 | YES | COMPLETE
PO-2024-1063 | 2024-06-11 | Steel Supplies | Materials and services for construction - Phase 3 | 16495 | 2024-07-07 | YES | CANCELLED
PO-2024-1064 | 2024-01-17 | Premium Plumbing | Materials and services for construction - Phase 2 | 28068 | 2024-02-16 | YES | COMPLETE
PO-2024-1065 | 2024-03-09 | Timber Traders | Materials and services for construction - Phase 1 | 54771 | 2024-04-03 | NO | COMPLETE
PO-2024-1066 | 2024-06-24 | Sydney Tiles | Materials and services for construction - Phase 3 | 43235 | 2024-07-05 | NO | COMPLETE
PO-2024-1067 | 2024-06-28 | Timber Traders | Materials and services for construction - Phase 5 | 68192 | 2024-07-25 | YES | COMPLETE
PO-2024-1068 | 2024-02-24 | Premium Plumbing | Materials and services for construction - Phase 2 | 52039 | 2024-03-10 | YES | CANCELLED
PO-2024-1069 | 2024-04-11 | Concrete Co | Materials and services for construction - Phase 1 | 40972 | 2024-05-04 | NO | COMPLETE
PO-2024-1070 | 2024-03-06 | Spark Electrical | Materials and services for construction - Phase 4 | 25422 | 2024-03-23 | YES | PENDING
PO-2024-1071 | 2024-03-10 | BuildMart | Materials and services for construction - Phase 4 | 47249 | 2024-04-02 | NO | COMPLETE
PO-2024-1072 | 2024-05-08 | Timber Traders | Materials and services for construction - Phase 3 | 70653 | 2024-06-05 | NO | COMPLETE
PO-2024-1073 | 2024-07-08 | BuildMart | Materials and services for construction - Phase 1 | 47342 | 2024-07-16 | YES | COMPLETE
PO-2024-1074 | 2024-04-17 | Spark Electrical | Materials and services for construction - Phase 2 | 8735 | 2024-05-02 | NO | PENDING
PO-2024-1075 | 2024-02-12 | BuildMart | Materials and services for construction - Phase 5 | 36081 | 2024-03-13 | NO | COMPLETE
PO-2024-1076 | 2024-02-22 | Concrete Co | Materials and services for construction - Phase 2 | 67334 | 2024-03-14 | YES | CANCELLED
PO-2024-1077 | 2024-04-11 | Ace Carpentry | Materials and services for construction - Phase 1 | 47221 | 2024-05-06 | YES | COMPLETE
PO-2024-1078 | 2024-03-12 | Pro Paint | Materials and services for construction - Phase 3 | 72730 | 2024-04-10 | YES | CANCELLED
PO-2024-1079 | 2024-06-02 | Premium Plumbing | Materials and services for construction - Phase 3 | 41508 | 2024-06-09 | NO | COMPLETE
PO-2024-1080 | 2024-07-18 | Spark Electrical | Materials and services for construction - Phase 1 | 64881 | 2024-07-31 | NO | COMPLETE
PO-2024-1081 | 2024-02-07 | Pro Paint | Materials and services for construction - Phase 1 | 76767 | 2024-03-04 | YES | COMPLETE
PO-2024-1082 | 2024-03-30 | BuildMart | Materials and services for construction - Phase 4 | 41413 | 2024-04-25 | YES | COMPLETE
PO-2024-1083 | 2024-03-31 | Steel Supplies | Materials and services for construction - Phase 2 | 17048 | 2024-04-28 | YES | CANCELLED
PO-2024-1084 | 2024-05-05 | BuildMart | Materials and services for construction - Phase 2 | 49688 | 2024-05-29 | YES | PENDING
PO-2024-1085 | 2024-07-22 | Concrete Co | Materials and services for construction - Phase 5 | 38316 | 2024-07-30 | YES | PENDING
PO-2024-1086 | 2024-01-24 | Ace Carpentry | Materials and services for construction - Phase 5 | 36653 | 2024-02-23 | YES | COMPLETE
PO-2024-1087 | 2024-01-12 | BuildMart | Materials and services for construction - Phase 5 | 20753 | 2024-02-04 | NO | COMPLETE
PO-2024-1088 | 2024-04-03 | Pro Paint | Materials and services for construction - Phase 2 | 76899 | 2024-04-15 | YES | COMPLETE
PO-2024-1089 | 2024-04-18 | Ace Carpentry | Materials and services for construction - Phase 2 | 38995 | 2024-05-13 | YES | COMPLETE
PO-2024-1090 | 2024-01-24 | Premium Plumbing | Materials and services for construction - Phase 2 | 12321 | 2024-02-18 | NO | COMPLETE
PO-2024-1091 | 2024-06-30 | Spark Electrical | Materials and services for construction - Phase 4 | 57212 | 2024-07-25 | YES | COMPLETE
PO-2024-1092 | 2024-02-06 | Ace Carpentry | Materials and services for construction - Phase 2 | 49732 | 2024-03-01 | YES | CANCELLED
PO-2024-1093 | 2024-04-28 | Premium Plumbing | Materials and services for construction - Phase 2 | 73515 | 2024-05-07 | YES | PENDING
PO-2024-1094 | 2024-06-16 | Sydney Tiles | Materials and services for construction - Phase 3 | 50312 | 2024-07-16 | NO | COMPLETE
PO-2024-1095 | 2024-05-21 | Spark Electrical | Materials and services for construction - Phase 5 | 40114 | 2024-06-11 | NO | COMPLETE
PO-2024-1096 | 2024-03-08 | Ace Carpentry | Materials and services for construction - Phase 5 | 71843 | 2024-03-24 | YES | PENDING
PO-2024-1097 | 2024-03-01 | Ace Carpentry | Materials and services for construction - Phase 3 | 38621 | 2024-03-12 | YES | PENDING
PO-2024-1098 | 2024-07-16 | Spark Electrical | Materials and services for construction - Phase 4 | 40312 | 2024-08-12 | YES | COMPLETE
PO-2024-1099 | 2024-04-13 | Concrete Co | Materials and services for construction - Phase 2 | 72816 | 2024-04-25 | YES | CANCELLED
PO-2024-1100 | 2024-05-14 | Steel Supplies | Materials and services for construction - Phase 5 | 7006 | 2024-05-25 | YES | PENDING

## Invoice Matching
PO TO INVOICE MATCHING
PO# | Invoice# | PO Amount | Invoice Amount | Variance | Notes
PO-2024-1000 | BH-2024-0847 | 2600 | 2868 | -268 | Incl. GST difference
PO-2024-1001 | RM-2024-8845 | 7200 | 7872 | -672 | Extra pump fees
PO-2024-1002 | SES-2024-3421 | 2400 | 2399 | 1 | OK
PO-2024-1003 | APS-2024-8912 | 3800 | 3872 | -72 | OK
PO-2024-1004 | TSC-INV-4421 | 5700 | 5759 | -59 | OK