## Payment Schedule
CLIENT PAYMENT SCHEDULE - PROJECT A | [6 empty] | GL Account | % Complete | Revenue Recognized | Deferred Revenue
[7 empty] | 4100 | 100%
Milestone | Invoice# | Description | Amount | Due Date | Paid Date | Status | 4100 | 100%
Deposit (10%) | INV-C-001 | Deposit on contract signing | 65000 | 2024-01-20 | 2024-01-18 | PAID | 4100 | 100%
Base/Slab (15%) | INV-C-002 | Completion of slab | 97500 | 2024-08-15 | 2024-08-12 | PAID | 4100 | 100%
Frame (20%) | INV-C-003 | Frame complete and roof on | 130000 | 2024-09-25 |  | OVERDUE | 4100 | 50%
Lock-up (20%) | INV-C-004 | Brickwork, windows, roof tiles | 130000 | TBC |  | NOT INVOICED | 4100 | 50%
Fixing (15%) | INV-C-005 | Internal fixing, plaster, paint | 97500 | TBC |  | NOT INVOICED | 4100 | 80%
Practical (15%) | INV-C-006 | Practical completion | 97500 | TBC |  | NOT INVOICED | 4100 | 100%
Final/Defects (5%) | INV-C-007 | Final completion + defects | 32500 | TBC |  | NOT INVOICED | 4100 | 100%
[7 empty] | 4100 | 100%
|  | TOTAL CONTRACT: | 650000 |  |  |  | 4100 | 100%
18160 | 6573 | Item 12 | 7963 | 1381 | 26374 | 31882 | 4100 | 100%
37618 | 26460 | Item 13 | 7010 | 20612 | 27927 | 27196 | 4100 | 100%
27833 | 18633 | Item 14 | 21888 | 15472 | 25573 | 49618 | 4100 | 100%
15770 | 2503 | Item 15 | 37233 | 22960 | 2986 | 40173 | 4100 | 100%
9048 | 45025 | Item 16 | 29667 | 3439 | 13596 | 20877 | 4100 | 50%
12859 | 41838 | Item 17 | 12626 | 48698 | 3151 | 37778 | 4100 | 100%
24749 | 18106 | Item 18 | 12273 | 41521 | 23261 | 16862 | 4100 | 80%
6538 | 23021 | Item 19 | 6157 | 30949 | 35606 | 8454 | 4100 | 50%
26376 | 48382 | Item 20 | 48962 | 49601 | 21327 | 45772 | 4100 | 100%
48891 | 26996 | Item 21 | 19584 | 44508 | 31275 | 25806 | 4100 | 100%
3295 | 11236 | Item 22 | 7108 | 7503 | 29940 | 23769 | 4100 | 50%
4791 | 16111 | Item 23 | 25068 | 34906 | 11061 | 21058 | 4100 | 100%
36488 | 7158 | Item 24 | 47711 | 22583 | 5916 | 25310 | 4100 | 100%
34735 | 12940 | Item 25 | 30667 | 49467 | 48075 | 15937 | 4100 | 100%
39729 | 29128 | Item 26 | 14530 | 33497 | 35034 | 33911 | 4100 | 50%
29505 | 10049 | Item 27 | 49910 | 4385 | 1716 | 23829 | 4100 | 50%
24574 | 46856 | Item 28 | 44563 | 29987 | 24217 | 47513 | 4100 | 80%
38365 | 35433 | Item 29 | 42097 | 20558 | 34350 | 42416 | 4100 | 50%
13560 | 33334 | Item 30 | 37282 | 18528 | 36632 | 20870 | 4100 | 80%
14101 | 25067 | Item 31 | 10532 | 24804 | 14535 | 28730 | 4100 | 50%
22979 | 32756 | Item 32 | 36970 | 3534 | 2186 | 45705 | 4100 | 80%
22975 | 2414 | Item 33 | 45583 | 19876 | 40813 | 46957 | 4100 | 80%
33724 | 4833 | Item 34 | 31278 | 41497 | 13157 | 15031 | 4100 | 100%
16900 | 49917 | Item 35 | 11757 | 45533 | 2108 | 36749 | 4100 | 100%
10823 | 29858 | Item 36 | 35856 | 22320 | 41895 | 31641 | 4100 | 80%
44664 | 12568 | Item 37 | 9695 | 39851 | 33690 | 7460 | 4100 | 80%
15799 | 4776 | Item 38 | 15621 | 28973 | 20650 | 37099 | 4100 | 50%
4328 | 48220 | Item 39 | 42378 | 6103 | 13122 | 20943 | 4100 | 80%
33519 | 19000 | Item 40 | 40180 | 37119 | 40408 | 43857 | 4100 | 100%
17840 | 23227 | Item 41 | 29881 | 10372 | 34728 | 24654 | 4100 | 100%
29865 | 21135 | Item 42 | 6158 | 9365 | 29895 | 5558 | 4100 | 50%
43042 | 42076 | Item 43 | 12746 | 9938 | 46347 | 1787 | 4100 | 100%
11439 | 34472 | Item 44 | 33389 | 9132 | 38957 | 9160 | 4100 | 50%

## Variations
CLIENT VARIATIONS REGISTER
VO# | Date | Description | Cost | Client Price | Status | Invoiced
VO-001 | 2024-08-15 | Kitchen benchtop upgrade to stone | 3682 | 4500 | APPROVED | YES
VO-002 | 2024-08-20 | Additional bedroom window | 982 | 1200 | APPROVED | NO
VO-003 | 2024-09-01 | Bathroom tile upgrade | 2291 | 2800 | APPROVED | NO
VO-004 | 2024-09-05 | Extra balcony waterproofing | 1227 | 1500 | APPROVED | NO
VO-005 | 2024-09-10 | Ducted AC upgrade from split | 2618 | 3200 | PENDING | NO
VO-006 | 2024-09-15 | Extra power points x8 | 785 | 960 | APPROVED | NO
REVENUE LEAKAGE: |  |  |  | 6460

## Communications
CLIENT COMMUNICATIONS
Date | Type | Subject | Notes
2024-08-15 | Email | Payment reminder | Sent invoice INV-C-002
2024-09-01 | Site Meeting | Variation requests | Discussed kitchen and bathroom upgrades
2024-09-25 | Email | Payment overdue | INV-C-003 now 5 days overdue - called client
2024-09-30 | Phone | Progress update | Frame complete, moving to lock-up phase