## Revenue Recognition
REVENUE RECOGNITION SCHEDULE
Percentage of Completion Method
Milestone | Contract Value | % Complete (Physical) | % Complete (Cost) | Revenue Earned | Revenue Billed | Deferred Revenue | Status
Site Preparation | 32500 | 100% | 100% |  | 32500 |  | COMPLETE
Foundation & Slab | 130000 | 100% | 100% |  | 130000 |  | COMPLETE
Framing & Structure | 195000 | 75% | 72% |  | 146250 |  | IN PROGRESS
Roof & Exterior | 97500 | 40% | 38% |  | 39000 |  | IN PROGRESS
Internal Fit-out | 130000 | 15% | 12% |  | 19500 |  | STARTED
Final Finishes | 65000 | 0% | 0% |  | 0 |  | NOT STARTED
TOTAL
Item 11 |  | 31193 | 26145 |  |  |  | 33205
Item 12 |  | 33689 | 47760 |  |  |  | 14582
Item 13 |  | 41098 | 35700 |  |  |  | 9706
Item 14 |  | 4984 | 2090 |  |  |  | 35063
Item 15 |  | 9735 | 19676 |  |  |  | 40648
Item 16 |  | 47256 | 31288 |  |  |  | 36749
Item 17 |  | 9808 | 39273 |  |  |  | 30311
Item 18 |  | 45273 | 6689 |  |  |  | 24156
Item 19 |  | 38127 | 8904 |  |  |  | 9229
Item 20 |  | 3247 | 39619 |  |  |  | 23398
Item 21 |  | 37156 | 11302 |  |  |  | 48545
Item 22 |  | 46150 | 17509 |  |  |  | 4437
Item 23 |  | 34994 | 37256 |  |  |  | 42465
Item 24 |  | 20003 | 22046 |  |  |  | 26326
Item 25 |  | 22473 | 19043 |  |  |  | 48410
Item 26 |  | 39644 | 8328 |  |  |  | 22631
Item 27 |  | 13735 | 34852 |  |  |  | 34479
Item 28 |  | 47596 | 46464 |  |  |  | 20264
Item 29 |  | 23888 | 4322 |  |  |  | 6823
Item 30 |  | 6069 | 46832 |  |  |  | 17980
Item 31 |  | 9734 | 47633 |  |  |  | 33395
Item 32 |  | 26572 | 20167 |  |  |  | 8170
Item 33 |  | 45649 | 8477 |  |  |  | 17176
Item 34 |  | 23336 | 7360 |  |  |  | 27694
Item 35 |  | 12707 | 8093 |  |  |  | 47534
Item 36 |  | 30768 | 9010 |  |  |  | 20991