## PO Register
PURCHASE ORDER REGISTER
PO# | Date | Supplier | Description | Amount | Delivery Date | Invoice Received | Status
PO-2024-1000 | 01/07/2024 | Spark Electrical | Electrical materials | 22080 | 12/07/2024 | YES | COMPLETE
PO-2024-1001 | 04/07/2024 | Aqua Plumbing | Plumbing supplies | 10764 | 23/07/2024 | YES | COMPLETE
PO-2024-1002 | 07/07/2024 | BuildMart | General supplies | 20411 | 26/07/2024 | YES | COMPLETE
PO-2024-1003 | 10/07/2024 | Tile Palace | Floor & wall tiles | 1734 | 28/07/2024 | NO | COMPLETE
PO-2024-1004 | 13/07/2024 | Timber Supplies Co | Structural timber | 4189 | 29/07/2024 | YES | COMPLETE
PO-2024-1005 | 16/07/2024 | Aqua Plumbing | Plumbing supplies | 2428 | 01/08/2024 | YES | COMPLETE
PO-2024-1006 | 19/07/2024 | Window World | Windows & doors | 19772 | 31/07/2024 | YES | COMPLETE
PO-2024-1007 | 22/07/2024 | Bob's Hardware | Timber & fixings | 1704 | 04/08/2024 | YES | COMPLETE
PO-2024-1008 | 25/07/2024 | Pacific Paint | Paint & materials | 13698 | 10/08/2024 | NO | DELIVERED
PO-2024-1009 | 28/07/2024 | Tile Palace | Floor & wall tiles | 15887 | 16/08/2024 | YES | COMPLETE
PO-2024-1010 | 31/07/2024 | Tile Palace | Floor & wall tiles | 20001 | 08/08/2024 | NO | COMPLETE
PO-2024-1011 | 03/08/2024 | BuildMart | General supplies | 24854 | 11/08/2024 | YES | PENDING
PO-2024-1012 | 06/08/2024 | Spark Electrical | Electrical materials | 13009 | 25/08/2024 | YES | PENDING
PO-2024-1013 | 09/08/2024 | Pacific Paint | Paint & materials | 16932 | 18/08/2024 | YES | COMPLETE
PO-2024-1014 | 12/08/2024 | Spark Electrical | Electrical materials | 15832 | 26/08/2024 | YES | COMPLETE
PO-2024-1015 | 15/08/2024 | Aqua Plumbing | Plumbing supplies | 10657 | 01/09/2024 | YES | COMPLETE
PO-2024-1016 | 18/08/2024 | Aqua Plumbing | Plumbing supplies | 6971 | 27/08/2024 | YES | COMPLETE
PO-2024-1017 | 21/08/2024 | BuildMart | General supplies | 2665 | 11/09/2024 | YES | COMPLETE
PO-2024-1018 | 24/08/2024 | Window World | Windows & doors | 16256 | 05/09/2024 | YES | COMPLETE
PO-2024-1019 | 27/08/2024 | Window World | Windows & doors | 24671 | 09/09/2024 | YES | COMPLETE
PO-2024-1020 | 30/08/2024 | Timber Supplies Co | Structural timber | 10469 | 10/09/2024 | YES | PENDING
PO-2024-1021 | 02/09/2024 | Spark Electrical | Electrical materials | 4077 | 15/09/2024 | YES | DELIVERED
PO-2024-1022 | 05/09/2024 | Spark Electrical | Electrical materials | 15482 | 16/09/2024 | NO | COMPLETE
PO-2024-1023 | 08/09/2024 | Steel Direct | Steel beams | 2061 | 26/09/2024 | YES | PENDING
PO-2024-1024 | 11/09/2024 | Window World | Windows & doors | 23355 | 27/09/2024 | YES | DELIVERED
PO-2024-1025 | 14/09/2024 | Steel Direct | Steel beams | 15954 | 01/10/2024 | NO | COMPLETE
PO-2024-1026 | 17/09/2024 | BuildMart | General supplies | 8871 | 25/09/2024 | YES | COMPLETE
PO-2024-1027 | 20/09/2024 | Tile Palace | Floor & wall tiles | 13995 | 06/10/2024 | YES | COMPLETE
PO-2024-1028 | 23/09/2024 | BuildMart | General supplies | 11014 | 04/10/2024 | YES | COMPLETE
PO-2024-1029 | 26/09/2024 | Bob's Hardware | Timber & fixings | 23425 | 04/10/2024 | NO | COMPLETE

## Invoice Matching
PO TO INVOICE MATCHING
PO# | Invoice# | PO Amount | Invoice Amount | Variance | Notes
PO-2024-1000 | BH-2024-0847 | 2600 | 2868 | -268 | Incl. GST difference
PO-2024-1001 | RM-2024-8845 | 7200 | 7872 | -672 | Extra pump fees
PO-2024-1002 | SES-2024-3421 | 2400 | 2399 | 1 | OK
PO-2024-1003 | APS-2024-8912 | 3800 | 3872 | -72 | OK
PO-2024-1004 | TSC-INV-4421 | 5700 | 5759 | -59 | OK