## Payment Schedule
CLIENT PAYMENT SCHEDULE - PROJECT A
Milestone | Invoice# | Description | Amount | Due Date | Paid Date | Status
Deposit (10%) | INV-C-001 | Deposit on contract signing | 65000 | 2024-01-20 | 2024-01-18 | PAID
Base/Slab (15%) | INV-C-002 | Completion of slab | 97500 | 2024-08-15 | 2024-08-12 | PAID
Frame (20%) | INV-C-003 | Frame complete and roof on | 130000 | 2024-09-25 |  | OVERDUE
Lock-up (20%) | INV-C-004 | Brickwork, windows, roof tiles | 130000 | TBC |  | NOT INVOICED
Fixing (15%) | INV-C-005 | Internal fixing, plaster, paint | 97500 | TBC |  | NOT INVOICED
Practical (15%) | INV-C-006 | Practical completion | 97500 | TBC |  | NOT INVOICED
Final/Defects (5%) | INV-C-007 | Final completion + defects | 32500 | TBC |  | NOT INVOICED
|  | TOTAL CONTRACT: | 650000

## Variations
CLIENT VARIATIONS REGISTER
VO# | Date | Description | Cost | Client Price | Status | Invoiced
VO-001 | 2024-08-15 | Kitchen benchtop upgrade to stone | 3682 | 4500 | APPROVED | YES
VO-002 | 2024-08-20 | Additional bedroom window | 982 | 1200 | APPROVED | NO
VO-003 | 2024-09-01 | Bathroom tile upgrade | 2291 | 2800 | APPROVED | NO
VO-004 | 2024-09-05 | Extra balcony waterproofing | 1227 | 1500 | APPROVED | NO
VO-005 | 2024-09-10 | Ducted AC upgrade from split | 2618 | 3200 | PENDING | NO
VO-006 | 2024-09-15 | Extra power points x8 | 785 | 960 | APPROVED | NO
REVENUE LEAKAGE: |  |  |  | 6460

## Communications
CLIENT COMMUNICATIONS
Date | Type | Subject | Notes
2024-08-15 | Email | Payment reminder | Sent invoice INV-C-002
2024-09-01 | Site Meeting | Variation requests | Discussed kitchen and bathroom upgrades
2024-09-25 | Email | Payment overdue | INV-C-003 now 5 days overdue - called client
2024-09-30 | Phone | Progress update | Frame complete, moving to lock-up phase