## Defects List
DEFECTS & SNAGGING LIST - PROJECT A
ID | Location | Trade | Description | Severity | Reported Date | Due Date | Status | Notes
D001 | Main Bathroom | Plumbing | Shower leak - needs waterproofing repair | CRITICAL | 2024-09-05 | 2024-09-12 | OVERDUE | Blocking handover!
D002 | Kitchen | Electrical | Power point not working | HIGH | 2024-09-10 | 2024-09-17 | IN PROGRESS | Electrician booked
D003 | Bedroom 2 | Painting | Touch up wall paint | LOW | 2024-09-15 | 2024-09-22 | PENDING
D004 | Living Room | Flooring | Timber floor scratch | MEDIUM | 2024-09-12 | 2024-09-19 | PENDING | Needs re-sanding
D005 | Front Entry | Carpentry | Door not closing properly | MEDIUM | 2024-09-08 | 2024-09-15 | FIXED | Adjusted hinges
D006 | Laundry | Plumbing | Tap dripping | LOW | 2024-09-18 | 2024-09-25 | PENDING
D007 | Garage | Electrical | Light switch faulty | LOW | 2024-09-16 | 2024-09-23 | PENDING
D008 | Master Bedroom | Plastering | Ceiling crack | MEDIUM | 2024-09-14 | 2024-09-21 | FIXED | Patched and painted
D009 | Bathroom 2 | Tiling | Grout needs cleaning | LOW | 2024-09-17 | 2024-09-24 | PENDING
D010 | External | Brickwork | Mortar spillage on paving | LOW | 2024-09-11 | 2024-09-18 | FIXED | Cleaned
D011 | Staircase | Carpentry | Handrail loose | HIGH | 2024-09-13 | 2024-09-20 | IN PROGRESS | Safety issue
D012 | Kitchen | Cabinets | Drawer not aligned | LOW | 2024-09-19 | 2024-09-26 | PENDING
D013 | Ensuite | Plumbing | Basin drain slow | MEDIUM | 2024-09-10 | 2024-09-17 | FIXED | Cleared
D014 | Living Room | Electrical | Downlight not centered | LOW | 2024-09-18 | 2024-09-25 | PENDING
D015 | External | Landscaping | Pavers uneven | MEDIUM | 2024-09-15 | 2024-09-22 | PENDING | Landscaper to fix
D016 | Bedroom 3 | Windows | Window hard to open | MEDIUM | 2024-09-12 | 2024-09-19 | FIXED | Adjusted
D017 | Kitchen | Benchtop | Small chip in stone | LOW | 2024-09-16 | 2024-09-23 | PENDING
D018 | Garage | Painting | Ceiling needs touch up | LOW | 2024-09-17 | 2024-09-24 | PENDING
D019 | External | Roof | Tile alignment issue | MEDIUM | 2024-09-09 | 2024-09-16 | FIXED | Re-laid tiles
D020 | Laundry | Cabinets | Door hinge squeaks | LOW | 2024-09-18 | 2024-09-25 | PENDING | Needs oil