## Subcontractors
789 Mountain View Terrace - Subcontractor Register
Company | Trade | Contact | Phone | Contract Value | Start Date | Status | Insurance
Elite Framing Solutions | Carpentry | James Robertson | 0428 765 432 | 125000 | 15-Sep-24 | In Progress | ✓
Alpine Plumbing Services | Plumbing | Robert Chen | 0412 543 876 | 68000 | 1-Oct-24 | Scheduled | ✓
PowerTech Electrical | Electrical | Sarah Mitchell | 0421 876 543 | 72000 | 15-Oct-24 | Scheduled | ✓
Mountain View Roofing | Roofing | Tom Wilson | 0438 234 567 | 52000 | 1-Nov-24 | Scheduled | ✓
Precision Tiling Co | Tiling | Maria Santos | 0434 567 890 | 48000 | 15-Jan-25 | Not Started | ✓