## Budget Tracker
789 Mountain View Terrace - Budget Tracker
Contract Value: $820,000 ¦ As of: 03 October 2025
Category | Budgeted | Committed | Spent | Variance | Status | % Used
Land Acquisition | 418215 | 418215 | 418215 | 0 | Complete
Design & Consultants | 75000 | 73550 | 73550 | 1450 | Complete
Permits & Approvals | 28000 | 26950 | 26950 | 1050 | Complete
Site Works | 73500 | 67330 | 67330 | 6170 | Complete
Foundations | 78000 | 46118 | 46118 | 31882 | Under Budget
Framing & Structure | 125000 | 75680 | 0 | 49320 | In Progress
Roofing | 52000 | 0 | 0 | 52000 | Not Started
External Cladding | 68000 | 0 | 0 | 68000 | Not Started
Windows & Doors | 85000 | 0 | 0 | 85000 | Not Started
Plumbing | 68000 | 24618 | 0 | 43382 | Materials Ordered
Electrical | 72000 | 0 | 0 | 72000 | Not Started
Insulation | 18000 | 0 | 0 | 18000 | Not Started
Plasterboard | 45000 | 0 | 0 | 45000 | Not Started
Tiling | 48000 | 0 | 0 | 48000 | Not Started
Kitchen | 55000 | 0 | 0 | 55000 | Not Started
Bathrooms | 48000 | 0 | 0 | 48000 | Not Started
Flooring | 42000 | 0 | 0 | 42000 | Not Started
Painting | 35000 | 0 | 0 | 35000 | Not Started
Cabinetry | 38000 | 0 | 0 | 38000 | Not Started
Fixtures & Fittings | 28000 | 0 | 0 | 28000 | Not Started
TOTAL