## PO Register
PURCHASE ORDER REGISTER
[8 empty] | Status | Count
PO# | Date | Supplier | Description | Amount | Delivery Date | Invoice Received | Status | COMPLETE
PO-2024-1000 | 01/07/2024 | Spark Electrical | Electrical materials | 22080 | 12/07/2024 | YES | COMPLETE | PENDING
PO-2024-1001 | 04/07/2024 | Aqua Plumbing | Plumbing supplies | 10764 | 23/07/2024 | YES | COMPLETE | CANCELLED
PO-2024-1002 | 07/07/2024 | BuildMart | General supplies | 20411 | 26/07/2024 | YES | COMPLETE
PO-2024-1003 | 10/07/2024 | Tile Palace | Floor & wall tiles | 1734 | 28/07/2024 | NO | COMPLETE
PO-2024-1004 | 13/07/2024 | Timber Supplies Co | Structural timber | 4189 | 29/07/2024 | YES | COMPLETE
PO-2024-1005 | 16/07/2024 | Aqua Plumbing | Plumbing supplies | 2428 | 01/08/2024 | YES | COMPLETE
PO-2024-1006 | 19/07/2024 | Window World | Windows & doors | 19772 | 31/07/2024 | YES | COMPLETE
PO-2024-1007 | 22/07/2024 | Bob's Hardware | Timber & fixings | 1704 | 04/08/2024 | YES | COMPLETE
PO-2024-1008 | 25/07/2024 | Pacific Paint | Paint & materials | 13698 | 10/08/2024 | NO | DELIVERED
PO-2024-1009 | 28/07/2024 | Tile Palace | Floor & wall tiles | 15887 | 16/08/2024 | YES | COMPLETE
PO-2024-1010 | 31/07/2024 | Tile Palace | Floor & wall tiles | 20001 | 08/08/2024 | NO | COMPLETE
PO-2024-1011 | 03/08/2024 | BuildMart | General supplies | 24854 | 11/08/2024 | YES | PENDING
PO-2024-1012 | 06/08/2024 | Spark Electrical | Electrical materials | 13009 | 25/08/2024 | YES | PENDING
PO-2024-1013 | 09/08/2024 | Pacific Paint | Paint & materials | 16932 | 18/08/2024 | YES | COMPLETE
PO-2024-1014 | 12/08/2024 | Spark Electrical | Electrical materials | 15832 | 26/08/2024 | YES | COMPLETE
PO-2024-1015 | 15/08/2024 | Aqua Plumbing | Plumbing supplies | 10657 | 01/09/2024 | YES | COMPLETE
PO-2024-1016 | 18/08/2024 | Aqua Plumbing | Plumbing supplies | 6971 | 27/08/2024 | YES | COMPLETE
PO-2024-1017 | 21/08/2024 | BuildMart | General supplies | 2665 | 11/09/2024 | YES | COMPLETE
PO-2024-1018 | 24/08/2024 | Window World | Windows & doors | 16256 | 05/09/2024 | YES | COMPLETE
PO-2024-1019 | 27/08/2024 | Window World | Windows & doors | 24671 | 09/09/2024 | YES | COMPLETE
PO-2024-1020 | 30/08/2024 | Timber Supplies Co | Structural timber | 10469 | 10/09/2024 | YES | PENDING
PO-2024-1021 | 02/09/2024 | Spark Electrical | Electrical materials | 4077 | 15/09/2024 | YES | DELIVERED
PO-2024-1022 | 05/09/2024 | Spark Electrical | Electrical materials | 15482 | 16/09/2024 | NO | COMPLETE
PO-2024-1023 | 08/09/2024 | Steel Direct | Steel beams | 2061 | 26/09/2024 | YES | PENDING
PO-2024-1024 | 11/09/2024 | Window World | Windows & doors | 23355 | 27/09/2024 | YES | DELIVERED
PO-2024-1025 | 14/09/2024 | Steel Direct | Steel beams | 15954 | 01/10/2024 | NO | COMPLETE
PO-2024-1026 | 17/09/2024 | BuildMart | General supplies | 8871 | 25/09/2024 | YES | COMPLETE
PO-2024-1027 | 20/09/2024 | Tile Palace | Floor & wall tiles | 13995 | 06/10/2024 | YES | COMPLETE
PO-2024-1028 | 23/09/2024 | BuildMart | General supplies | 11014 | 04/10/2024 | YES | COMPLETE
PO-2024-1031 | 2024-07-08 | Premium Plumbing | Materials and services for construction - Phase 3 | 64305 | 2024-07-15 | YES | COMPLETE
PO-2024-1032 | 2024-02-19 | Sydney Tiles | Materials and services for construction - Phase 4 | 58112 | 2024-03-17 | YES | COMPLETE
PO-2024-1033 | 2024-07-28 | Timber Traders | Materials and services for construction - Phase 4 | 11578 | 2024-08-13 | YES | COMPLETE
PO-2024-1034 | 2024-01-31 | Premium Plumbing | Materials and services for construction - Phase 3 | 52905 | 2024-02-21 | YES | CANCELLED
PO-2024-1035 | 2024-03-05 | BuildMart | Materials and services for construction - Phase 2 | 56898 | 2024-03-20 | YES | COMPLETE
PO-2024-1036 | 2024-01-23 | BuildMart | Materials and services for construction - Phase 5 | 19688 | 2024-02-21 | NO | COMPLETE
PO-2024-1037 | 2024-03-30 | Spark Electrical | Materials and services for construction - Phase 2 | 48427 | 2024-04-20 | YES | COMPLETE
PO-2024-1038 | 2024-03-06 | Spark Electrical | Materials and services for construction - Phase 3 | 15368 | 2024-03-13 | NO | COMPLETE
PO-2024-1039 | 2024-05-31 | Ace Carpentry | Materials and services for construction - Phase 1 | 58191 | 2024-06-13 | YES | COMPLETE
PO-2024-1040 | 2024-06-13 | BuildMart | Materials and services for construction - Phase 1 | 18042 | 2024-07-12 | NO | PENDING
PO-2024-1041 | 2024-03-01 | Spark Electrical | Materials and services for construction - Phase 4 | 59554 | 2024-03-21 | YES | COMPLETE
PO-2024-1042 | 2024-04-05 | Concrete Co | Materials and services for construction - Phase 2 | 15406 | 2024-05-01 | YES | CANCELLED
PO-2024-1043 | 2024-02-10 | Ace Carpentry | Materials and services for construction - Phase 2 | 79629 | 2024-03-02 | YES | PENDING
PO-2024-1044 | 2024-03-23 | Timber Traders | Materials and services for construction - Phase 2 | 31746 | 2024-04-20 | NO | COMPLETE
PO-2024-1045 | 2024-02-24 | Concrete Co | Materials and services for construction - Phase 1 | 51752 | 2024-03-25 | NO | COMPLETE
PO-2024-1046 | 2024-01-11 | Concrete Co | Materials and services for construction - Phase 3 | 22718 | 2024-01-26 | YES | CANCELLED
PO-2024-1047 | 2024-03-07 | Ace Carpentry | Materials and services for construction - Phase 2 | 39049 | 2024-03-20 | NO | COMPLETE
PO-2024-1048 | 2024-03-03 | Ace Carpentry | Materials and services for construction - Phase 2 | 38380 | 2024-03-28 | YES | COMPLETE
PO-2024-1049 | 2024-04-24 | Premium Plumbing | Materials and services for construction - Phase 3 | 12199 | 2024-05-24 | YES | COMPLETE
PO-2024-1050 | 2024-01-28 | Concrete Co | Materials and services for construction - Phase 4 | 25123 | 2024-02-24 | YES | COMPLETE
PO-2024-1051 | 2024-01-24 | Ace Carpentry | Materials and services for construction - Phase 5 | 35545 | 2024-02-14 | YES | COMPLETE
PO-2024-1052 | 2024-05-09 | Sydney Tiles | Materials and services for construction - Phase 3 | 5420 | 2024-05-27 | YES | CANCELLED
PO-2024-1053 | 2024-04-23 | BuildMart | Materials and services for construction - Phase 1 | 67212 | 2024-05-16 | YES | COMPLETE
PO-2024-1054 | 2024-06-04 | Timber Traders | Materials and services for construction - Phase 1 | 38560 | 2024-06-25 | NO | PENDING
PO-2024-1055 | 2024-03-26 | Spark Electrical | Materials and services for construction - Phase 5 | 16557 | 2024-04-07 | NO | CANCELLED
PO-2024-1056 | 2024-03-19 | BuildMart | Materials and services for construction - Phase 5 | 26878 | 2024-04-12 | YES | COMPLETE
PO-2024-1057 | 2024-06-07 | Sydney Tiles | Materials and services for construction - Phase 2 | 71499 | 2024-07-02 | YES | CANCELLED
PO-2024-1058 | 2024-05-12 | BuildMart | Materials and services for construction - Phase 5 | 40368 | 2024-06-11 | YES | CANCELLED
PO-2024-1059 | 2024-03-17 | Pro Paint | Materials and services for construction - Phase 2 | 69340 | 2024-04-11 | YES | COMPLETE
PO-2024-1060 | 2024-07-15 | BuildMart | Materials and services for construction - Phase 2 | 8460 | 2024-08-05 | YES | CANCELLED
PO-2024-1061 | 2024-03-18 | Steel Supplies | Materials and services for construction - Phase 5 | 68469 | 2024-04-01 | YES | COMPLETE
PO-2024-1062 | 2024-03-07 | Spark Electrical | Materials and services for construction - Phase 4 | 62034 | 2024-03-14 | NO | COMPLETE
PO-2024-1063 | 2024-01-26 | Sydney Tiles | Materials and services for construction - Phase 3 | 29093 | 2024-02-15 | YES | COMPLETE
PO-2024-1064 | 2024-04-15 | Sydney Tiles | Materials and services for construction - Phase 3 | 72440 | 2024-05-04 | YES | COMPLETE
PO-2024-1065 | 2024-04-12 | BuildMart | Materials and services for construction - Phase 5 | 35377 | 2024-05-05 | NO | COMPLETE
PO-2024-1066 | 2024-06-01 | Timber Traders | Materials and services for construction - Phase 1 | 59679 | 2024-06-27 | NO | COMPLETE
PO-2024-1067 | 2024-07-26 | BuildMart | Materials and services for construction - Phase 5 | 58894 | 2024-08-02 | YES | COMPLETE
PO-2024-1068 | 2024-06-01 | Sydney Tiles | Materials and services for construction - Phase 3 | 75717 | 2024-06-22 | YES | COMPLETE
PO-2024-1069 | 2024-01-13 | Sydney Tiles | Materials and services for construction - Phase 2 | 39522 | 2024-02-02 | YES | COMPLETE
PO-2024-1070 | 2024-07-07 | Ace Carpentry | Materials and services for construction - Phase 1 | 57266 | 2024-07-26 | NO | COMPLETE
PO-2024-1071 | 2024-07-06 | BuildMart | Materials and services for construction - Phase 3 | 51096 | 2024-07-28 | NO | COMPLETE
PO-2024-1072 | 2024-04-23 | Ace Carpentry | Materials and services for construction - Phase 3 | 71828 | 2024-05-09 | YES | PENDING
PO-2024-1073 | 2024-01-27 | Spark Electrical | Materials and services for construction - Phase 5 | 56973 | 2024-02-20 | YES | PENDING
PO-2024-1074 | 2024-02-02 | Sydney Tiles | Materials and services for construction - Phase 3 | 42932 | 2024-02-14 | YES | COMPLETE
PO-2024-1075 | 2024-04-15 | Pro Paint | Materials and services for construction - Phase 4 | 10631 | 2024-05-14 | YES | COMPLETE
PO-2024-1076 | 2024-01-23 | Premium Plumbing | Materials and services for construction - Phase 4 | 21937 | 2024-02-14 | YES | PENDING
PO-2024-1077 | 2024-04-17 | Steel Supplies | Materials and services for construction - Phase 2 | 30137 | 2024-04-26 | YES | COMPLETE
PO-2024-1078 | 2024-04-19 | Ace Carpentry | Materials and services for construction - Phase 1 | 72615 | 2024-05-09 | YES | PENDING
PO-2024-1079 | 2024-01-11 | Sydney Tiles | Materials and services for construction - Phase 3 | 75864 | 2024-02-04 | YES | CANCELLED
PO-2024-1080 | 2024-01-26 | BuildMart | Materials and services for construction - Phase 3 | 57260 | 2024-02-20 | NO | PENDING
PO-2024-1081 | 2024-05-13 | Timber Traders | Materials and services for construction - Phase 5 | 60820 | 2024-06-04 | NO | CANCELLED
PO-2024-1082 | 2024-02-22 | Sydney Tiles | Materials and services for construction - Phase 2 | 41773 | 2024-03-07 | YES | COMPLETE
PO-2024-1083 | 2024-05-11 | BuildMart | Materials and services for construction - Phase 1 | 64136 | 2024-06-04 | YES | COMPLETE
PO-2024-1084 | 2024-04-08 | Concrete Co | Materials and services for construction - Phase 1 | 31430 | 2024-04-23 | YES | COMPLETE
PO-2024-1085 | 2024-05-20 | Timber Traders | Materials and services for construction - Phase 3 | 11512 | 2024-06-13 | YES | COMPLETE
PO-2024-1086 | 2024-03-07 | Pro Paint | Materials and services for construction - Phase 3 | 41065 | 2024-03-19 | YES | CANCELLED
PO-2024-1087 | 2024-05-22 | Spark Electrical | Materials and services for construction - Phase 3 | 10044 | 2024-06-02 | YES | COMPLETE
PO-2024-1088 | 2024-04-24 | Steel Supplies | Materials and services for construction - Phase 1 | 56915 | 2024-05-08 | YES | COMPLETE
PO-2024-1089 | 2024-05-22 | BuildMart | Materials and services for construction - Phase 2 | 17453 | 2024-06-19 | YES | CANCELLED
PO-2024-1090 | 2024-01-18 | Premium Plumbing | Materials and services for construction - Phase 5 | 10555 | 2024-02-14 | YES | COMPLETE
PO-2024-1091 | 2024-04-29 | Sydney Tiles | Materials and services for construction - Phase 4 | 25937 | 2024-05-15 | NO | COMPLETE
PO-2024-1092 | 2024-01-27 | Premium Plumbing | Materials and services for construction - Phase 5 | 13412 | 2024-02-25 | YES | COMPLETE
PO-2024-1093 | 2024-03-07 | Timber Traders | Materials and services for construction - Phase 1 | 58890 | 2024-04-04 | NO | CANCELLED
PO-2024-1094 | 2024-02-17 | Timber Traders | Materials and services for construction - Phase 4 | 15725 | 2024-03-03 | YES | COMPLETE
PO-2024-1095 | 2024-05-23 | Concrete Co | Materials and services for construction - Phase 3 | 9953 | 2024-06-22 | YES | COMPLETE
PO-2024-1096 | 2024-04-27 | Timber Traders | Materials and services for construction - Phase 4 | 43077 | 2024-05-12 | YES | COMPLETE
PO-2024-1097 | 2024-06-26 | Concrete Co | Materials and services for construction - Phase 4 | 15059 | 2024-07-25 | YES | COMPLETE
PO-2024-1098 | 2024-03-09 | Timber Traders | Materials and services for construction - Phase 2 | 71144 | 2024-03-31 | YES | PENDING
PO-2024-1099 | 2024-05-07 | Timber Traders | Materials and services for construction - Phase 3 | 19400 | 2024-05-19 | YES | COMPLETE
PO-2024-1100 | 2024-04-08 | Steel Supplies | Materials and services for construction - Phase 2 | 31945 | 2024-04-26 | YES | COMPLETE

## Invoice Matching
PO TO INVOICE MATCHING
PO# | Invoice# | PO Amount | Invoice Amount | Variance | Notes
PO-2024-1000 | BH-2024-0847 | 2600 | 2868 | -268 | Incl. GST difference
PO-2024-1001 | RM-2024-8845 | 7200 | 7872 | -672 | Extra pump fees
PO-2024-1002 | SES-2024-3421 | 2400 | 2399 | 1 | OK
PO-2024-1003 | APS-2024-8912 | 3800 | 3872 | -72 | OK
PO-2024-1004 | TSC-INV-4421 | 5700 | 5759 | -59 | OK