## Revenue Recognition
REVENUE RECOGNITION SCHEDULE
Percentage of Completion Method
Milestone | Contract Value | % Complete (Physical) | % Complete (Cost) | Revenue Earned | Revenue Billed | Deferred Revenue | Status
Site Preparation | 32500 | 100% | 100% |  | 32500 |  | COMPLETE
Foundation & Slab | 130000 | 100% | 100% |  | 130000 |  | COMPLETE
Framing & Structure | 195000 | 75% | 72% |  | 146250 |  | IN PROGRESS
Roof & Exterior | 97500 | 40% | 38% |  | 39000 |  | IN PROGRESS
Internal Fit-out | 130000 | 15% | 12% |  | 19500 |  | STARTED
Final Finishes | 65000 | 0% | 0% |  | 0 |  | NOT STARTED
TOTAL