## Dashboard
PROJECT BUDGET DASHBOARD
Total Contract Value | 650000 | Total Spent
Budget Remaining |  | % Complete

## Budget Summary
PROJECT A - 123 SUNSET BOULEVARD - MASTER BUDGET
Contract Value: $650,000
Category | GL Account | Description | Budget | Actual Spent | Committed | Forecast | Variance | % Complete | Notes
LAND | 6100 | Land Purchase | 250000 | 250000 | 0 | 250000 | 0 | 100 | PAID
LAND | 6100 | Stamp Duty | 20000 | 20000 | 0 | 20000 | 0 | 100
LAND | 6100 | Legal Fees - Conveyancing | 3500 | 3500 | 0 | 3500 | 0 | 100
LAND | 6100 | Building Consultant Inspection | 850 | 850 | 0 | 850 | 0 | 100
LAND | 6100 | Soil Testing & Reports | 2200 | 2200 | 0 | 2200 | 0 | 100
DESIGN | 6200 | Architectural Plans | 15000 | 15000 | 0 | 15000 | 0 | 100
DESIGN | 6200 | Structural Engineer | 4500 | 4500 | 0 | 4500 | 0 | 100
DESIGN | 6200 | Building Surveyor | 3200 | 3200 | 0 | 3200 | 0 | 100
DESIGN | 6200 | Energy Rating Assessment | 850 | 850 | 0 | 850 | 0 | 100
DESIGN | 6200 | Development Application | 2800 | 2800 | 0 | 2800 | 0 | 100
DESIGN | 6200 | Building Permit | 1850 | 1850 | 0 | 1850 | 0 | 100
DESIGN | 6200 | Section 94 Contributions | 8500 | 8500 | 0 | 8500 | 0 | 100 | Paid to Council
DESIGN | 6200 | Design Revisions | 2000 | 2740 | 0 | 2740 | -740 | 100 | OVER BUDGET - Client changes
SITE PREP | 5500 | Site Survey | 1800 | 1800 | 0 | 1800 | 0 | 100
SITE PREP | 5500 | Demolition Existing Structures | 8500 | 8500 | 0 | 8500 | 0 | 100
SITE PREP | 5500 | Excavation & Earthworks | 10500 | 10920 | 0 | 10920 | -420 | 100 | Extra excavation needed
SITE PREP | 5500 | Temporary Fencing | 1200 | 1200 | 0 | 1200 | 0 | 100
SITE PREP | 5500 | Temporary Power & Water | 2800 | 2800 | 0 | 2800 | 0 | 100
SITE PREP | 5500 | Site Amenities & Toilet | 1450 | 1450 | 0 | 1450 | 0 | 100
FOUNDATION |  | Concrete - Footings | 8500 | 8500 | 0 | 8500 | 0 | 100
FOUNDATION |  | Concrete - Slab | 18200 | 18200 | 0 | 18200 | 0 | 100
FOUNDATION |  | Steel Reinforcement | 6800 | 6800 | 0 | 6800 | 0 | 100
FOUNDATION |  | Waterproofing Membrane | 2600 | 3490 | 0 | 3490 | -890 | 100 | Extra waterproofing req'd
FOUNDATION |  | Pier Holes & Concrete Pumping | 3200 | 3200 | 0 | 3200 | 0 | 100
FOUNDATION |  | Termite Barrier | 1800 | 1800 | 0 | 1800 | 0 | 100
FOUNDATION |  | Slab Polishing | 4200 | 4200 | 0 | 4200 | 0 | 100
FOUNDATION |  | Inspections & Testing | 900 | 900 | 0 | 900 | 0 | 100
FRAME |  | Timber Frame - Walls | 28500 | 28500 | 0 | 28500 | 0 | 95
FRAME |  | Roof Trusses | 12000 | 12000 | 0 | 12000 | 0 | 95
FRAME |  | Sarking & Bracing | 6200 | 6200 | 0 | 6200 | 0 | 95
FRAME |  | Steel Beams & Lintels | 8400 | 8400 | 0 | 8400 | 0 | 100
FRAME |  | Structural Inspections | 1200 | 1200 | 0 | 1200 | 0 | 95
FRAME |  | Scaffolding Hire | 4200 | 4200 | 0 | 4200 | 0 | 90
FRAME |  | Crane Hire | 1400 | 1400 | 0 | 1400 | 0 | 100
EXTERNAL |  | Brickwork - Face Brick | 42500 | 42500 | 0 | 42500 | 0 | 100
EXTERNAL |  | Windows & Doors | 18500 | 18500 | 0 | 18500 | 0 | 100
EXTERNAL |  | Roof Tiles | 15800 | 15800 | 0 | 15800 | 0 | 95
EXTERNAL |  | Ridge Capping & Flashing | 2850 | 2850 | 0 | 2850 | 0 | 95
EXTERNAL |  | Gutters & Downpipes | 1800 | 0 | 1800 | 1800 | 0 | 0 | NOT YET INVOICED
EXTERNAL |  | External Cladding | 8200 | 0 | 8200 | 8200 | 0 | 0 | Materials on site
EXTERNAL |  | Garage Door | 2800 | 0 | 2800 | 2800 | 0 | 0 | Ordered
EXTERNAL |  | External Paint | 6500 | 0 | 0 | 6500 | 0 | 0 | Not started
EXTERNAL |  | Balustrades | 4200 | 0 | 0 | 4200 | 0 | 0 | Not started
SERVICES |  | Plumbing - Rough In | 8500 | 8500 | 0 | 8500 | 0 | 100
SERVICES |  | Plumbing - Fixtures | 6200 | 0 | 6200 | 6780 | -580 | 0 | OVER - Client upgrade
SERVICES |  | Hot Water System | 2450 | 0 | 2450 | 2450 | 0 | 0 | Ordered
SERVICES |  | Electrical - Rough In | 12000 | 12000 | 0 | 12000 | 0 | 100
SERVICES |  | Electrical - Second Fix | 8500 | 0 | 8500 | 9740 | -1240 | 0 | OVER - Extra points
SERVICES |  | Light Fittings | 4200 | 0 | 0 | 4200 | 0 | 0 | Not selected yet
SERVICES |  | HVAC System | 12500 | 0 | 12500 | 12500 | 0 | 0 | Ducted AC installed
SERVICES |  | Solar Panels & Inverter | 8500 | 0 | 0 | 8500 | 0 | 0 | Not started
SERVICES |  | NBN & Communications | 1200 | 0 | 0 | 1200 | 0 | 0
SERVICES |  | Security System | 2800 | 0 | 0 | 2800 | 0 | 0
INTERNAL |  | Plasterboard & Cornice | 20350 | 0 | 20350 | 20350 | 0 | 0 | Booked for Oct
INTERNAL |  | Internal Painting | 14500 | 0 | 0 | 14500 | 0 | 0 | After plaster
INTERNAL |  | Kitchen Cabinets | 28000 | 0 | 0 | 30100 | -2100 | 0 | OVER - Client upgrade NOT INVOICED
INTERNAL |  | Kitchen Benchtops - Stone | 8500 | 0 | 0 | 8500 | 0 | 0
INTERNAL |  | Bathroom Vanities | 5200 | 0 | 0 | 5200 | 0 | 0
INTERNAL |  | Tiling - Bathrooms & Kitchen | 12300 | 0 | 0 | 12300 | 0 | 0
INTERNAL |  | Timber Flooring | 18500 | 0 | 0 | 18500 | 0 | 0
INTERNAL |  | Carpet | 8200 | 0 | 0 | 8200 | 0 | 0
INTERNAL |  | Internal Doors & Hardware | 6800 | 0 | 0 | 6800 | 0 | 0
INTERNAL |  | Wardrobe Fitouts | 9200 | 0 | 0 | 9200 | 0 | 0
INTERNAL |  | Splashbacks | 2400 | 0 | 0 | 2400 | 0 | 0
INTERNAL |  | Laundry Fitout | 3200 | 0 | 0 | 3200 | 0 | 0
EXTERNAL WORKS |  | Driveway - Concrete | 8500 | 0 | 0 | 8500 | 0 | 0
EXTERNAL WORKS |  | Fencing | 12500 | 0 | 0 | 12500 | 0 | 0
EXTERNAL WORKS |  | Landscaping | 6800 | 0 | 0 | 6800 | 0 | 0
EXTERNAL WORKS |  | Retaining Walls | 8200 | 0 | 0 | 8200 | 0 | 0
EXTERNAL WORKS |  | Letterbox & Entry | 1200 | 0 | 0 | 1200 | 0 | 0
EXTERNAL WORKS |  | External Lighting | 2400 | 0 | 0 | 2400 | 0 | 0
PROFESSIONAL |  | Building Insurance | 4200 | 4200 | 0 | 4200 | 0 | 100
PROFESSIONAL |  | Project Management | 8500 | 6330 | 2170 | 8500 | 0 | 75 | Monthly fees
PROFESSIONAL |  | Site Supervisor | 12000 | 9000 | 3000 | 12000 | 0 | 75 | Weekly fees
PROFESSIONAL |  | Council Fees & Inspections | 2800 | 2800 | 0 | 2800 | 0 | 100
TOTAL |  |  | 650000

## Cost Detail
DETAILED COST TRANSACTIONS
Date | Supplier | Invoice# | Description | Category | Amount | GST | Total | Status
15/01/2024 | Smith Family Trust | INV-1000 | Land Purchase | LAND | 250000 | 25000 | 275000 | OUTSTANDING
22/01/2024 | State Revenue Office | INV-1001 | Stamp Duty | LAND | 20000 | 2000 | 22000 | PAID
29/01/2024 | Johnson & Partners Legal | INV-1002 | Legal Fees | LAND | 3500 | 350 | 3850 | OUTSTANDING
05/02/2024 | Building Check Australia | INV-1003 | Inspection | LAND | 850 | 85 | 935 | PAID
12/02/2024 | Geotech Solutions | INV-1004 | Soil Test | LAND | 2200 | 220 | 2420 | OUTSTANDING
19/02/2024 | Design Studio | INV-1005 | Architect | DESIGN | 15000 | 1500 | 16500 | PAID
26/02/2024 | Structural Solutions | INV-1006 | Engineer | DESIGN | 4500 | 450 | 4950 | PAID
04/03/2024 | ABC Building Surveyors | INV-1007 | Surveyor | DESIGN | 3200 | 320 | 3520 | PAID
11/03/2024 | BigDig Excavations | INV-1008 | Excavation | SITE PREP | 10920 | 1092 | 12012 | PAID
2024-02-22 | Steel Supplies | INV-2024000 | Construction materials and services - Steel Supplies | Materials | 36949 |  |  | PAID
2024-01-17 | Premium Plumbing | INV-2024001 | Construction materials and services - Premium Plumbing | Subcontractors | 46944 |  |  | PAID
2024-07-10 | Pro Paint | INV-2024002 | Construction materials and services - Pro Paint | Materials | 44864 |  |  | PAID
2024-01-26 | Ace Carpentry | INV-2024003 | Construction materials and services - Ace Carpentry | Subcontractors | 18102 |  |  | OUTSTANDING
2024-04-11 | Spark Electrical | INV-2024004 | Construction materials and services - Spark Electrical | Land | 9236 |  |  | PAID
2024-03-03 | Spark Electrical | INV-2024005 | Construction materials and services - Spark Electrical | Labour | 6393 |  |  | PAID
2024-05-01 | Steel Supplies | INV-2024006 | Construction materials and services - Steel Supplies | Labour | 42886 |  |  | PAID
2024-04-18 | BuildMart | INV-2024007 | Construction materials and services - BuildMart | Equipment | 1838 |  |  | PAID
2024-07-09 | Premium Plumbing | INV-2024008 | Construction materials and services - Premium Plumbing | Equipment | 30313 |  |  | PAID
2024-05-10 | Ace Carpentry | INV-2024009 | Construction materials and services - Ace Carpentry | Materials | 48449 |  |  | OUTSTANDING
2024-03-25 | Spark Electrical | INV-2024010 | Construction materials and services - Spark Electrical | Subcontractors | 49519 |  |  | OUTSTANDING
2024-03-25 | Pro Paint | INV-2024011 | Construction materials and services - Pro Paint | Subcontractors | 29853 |  |  | PAID
2024-02-27 | Pro Paint | INV-2024012 | Construction materials and services - Pro Paint | Materials | 34886 |  |  | PAID
2024-06-22 | Premium Plumbing | INV-2024013 | Construction materials and services - Premium Plumbing | Labour | 44206 |  |  | PAID
2024-07-03 | Concrete Co | INV-2024014 | Construction materials and services - Concrete Co | Land | 28009 |  |  | OUTSTANDING
2024-03-04 | Concrete Co | INV-2024015 | Construction materials and services - Concrete Co | Subcontractors | 7206 |  |  | PAID
2024-02-15 | Steel Supplies | INV-2024016 | Construction materials and services - Steel Supplies | Subcontractors | 25783 |  |  | PAID
2024-02-08 | Steel Supplies | INV-2024017 | Construction materials and services - Steel Supplies | Materials | 24897 |  |  | PAID
2024-05-07 | Ace Carpentry | INV-2024018 | Construction materials and services - Ace Carpentry | Labour | 39680 |  |  | PAID
2024-06-01 | Smith Family Trust | INV-2024019 | Construction materials and services - Smith Family Trust | Equipment | 46172 |  |  | OUTSTANDING
2024-03-02 | Pro Paint | INV-2024020 | Construction materials and services - Pro Paint | Materials | 49161 |  |  | PAID
2024-02-27 | Smith Family Trust | INV-2024021 | Construction materials and services - Smith Family Trust | Land | 39131 |  |  | PAID
2024-05-03 | Ace Carpentry | INV-2024022 | Construction materials and services - Ace Carpentry | Equipment | 40956 |  |  | PAID
2024-07-04 | Smith Family Trust | INV-2024023 | Construction materials and services - Smith Family Trust | Subcontractors | 43019 |  |  | PAID
2024-01-30 | Spark Electrical | INV-2024024 | Construction materials and services - Spark Electrical | Labour | 45560 |  |  | PAID
2024-04-19 | Steel Supplies | INV-2024025 | Construction materials and services - Steel Supplies | Equipment | 47915 |  |  | OUTSTANDING
2024-03-31 | Concrete Co | INV-2024026 | Construction materials and services - Concrete Co | Materials | 24134 |  |  | OUTSTANDING
2024-05-28 | BuildMart | INV-2024027 | Construction materials and services - BuildMart | Equipment | 41511 |  |  | OUTSTANDING
2024-04-30 | Premium Plumbing | INV-2024028 | Construction materials and services - Premium Plumbing | Equipment | 32385 |  |  | PAID
2024-06-16 | Ace Carpentry | INV-2024029 | Construction materials and services - Ace Carpentry | Land | 5953 |  |  | PAID
2024-05-31 | Pro Paint | INV-2024030 | Construction materials and services - Pro Paint | Land | 1726 |  |  | PAID
2024-05-09 | Pro Paint | INV-2024031 | Construction materials and services - Pro Paint | Subcontractors | 35288 |  |  | OUTSTANDING
2024-05-24 | Concrete Co | INV-2024032 | Construction materials and services - Concrete Co | Materials | 45585 |  |  | OUTSTANDING
2024-06-20 | Ace Carpentry | INV-2024033 | Construction materials and services - Ace Carpentry | Equipment | 48335 |  |  | PAID
2024-04-28 | Ace Carpentry | INV-2024034 | Construction materials and services - Ace Carpentry | Labour | 41768 |  |  | PAID
2024-03-03 | BuildMart | INV-2024035 | Construction materials and services - BuildMart | Labour | 43906 |  |  | OUTSTANDING
2024-05-30 | Spark Electrical | INV-2024036 | Construction materials and services - Spark Electrical | Materials | 22525 |  |  | PAID
2024-04-22 | BuildMart | INV-2024037 | Construction materials and services - BuildMart | Equipment | 11632 |  |  | PAID
2024-06-22 | Spark Electrical | INV-2024038 | Construction materials and services - Spark Electrical | Equipment | 5988 |  |  | OUTSTANDING
2024-04-03 | Ace Carpentry | INV-2024039 | Construction materials and services - Ace Carpentry | Materials | 31131 |  |  | PAID
2024-06-24 | BuildMart | INV-2024040 | Construction materials and services - BuildMart | Equipment | 39814 |  |  | PAID
2024-06-21 | Premium Plumbing | INV-2024041 | Construction materials and services - Premium Plumbing | Materials | 43716 |  |  | OUTSTANDING
2024-03-22 | Premium Plumbing | INV-2024042 | Construction materials and services - Premium Plumbing | Land | 18419 |  |  | OUTSTANDING
2024-06-25 | Sydney Tiles | INV-2024043 | Construction materials and services - Sydney Tiles | Land | 46889 |  |  | PAID
2024-04-11 | Steel Supplies | INV-2024044 | Construction materials and services - Steel Supplies | Labour | 8208 |  |  | PAID
2024-02-11 | Steel Supplies | INV-2024045 | Construction materials and services - Steel Supplies | Subcontractors | 22684 |  |  | OUTSTANDING
2024-05-02 | Steel Supplies | INV-2024046 | Construction materials and services - Steel Supplies | Labour | 8899 |  |  | OUTSTANDING
2024-06-14 | Premium Plumbing | INV-2024047 | Construction materials and services - Premium Plumbing | Materials | 7145 |  |  | OUTSTANDING
2024-04-16 | Premium Plumbing | INV-2024048 | Construction materials and services - Premium Plumbing | Equipment | 26227 |  |  | PAID
2024-07-12 | BuildMart | INV-2024049 | Construction materials and services - BuildMart | Labour | 24145 |  |  | PAID

## Cashflow
WEEKLY CASHFLOW FORECAST
2024-01-22 | 0 | 43175 | 56825
2024-01-29 | 82341 | 37903
2024-02-05 | 128063 | 48440
2024-02-12 | 118094 | 35445
2024-02-19 | 100901 | 76410
2024-02-26 | 64575 | 67471
2024-03-04 | 103092 | 65542
2024-03-11 | 107703 | 64940
2024-03-18 | 62384 | 35284
2024-03-25 | 83638 | 58653
2024-04-01 | 82136 | 68469
2024-04-08 | 113954 | 55278
2024-04-15 | 90189 | 44981
2024-04-22 | 96387 | 47811
2024-04-29 | 56756 | 45229
2024-05-06 | 105977 | 45536
2024-05-13 | 100348 | 30790
2024-05-20 | 63219 | 76737
2024-05-27 | 83897 | 30938
2024-06-03 | 98749 | 55513
2024-06-10 | 140375 | 63850
2024-06-17 | 84585 | 70450
2024-06-24 | 71858 | 41964
2024-07-01 | 120067 | 75910
2024-07-08 | 147955 | 69993
2024-07-15 | 102076 | 47259
2024-07-22 | 53361 | 73525
2024-07-29 | 115576 | 53147
2024-08-05 | 62197 | 40210
2024-08-12 | 55862 | 47892
2024-08-19 | 131724 | 37124
2024-08-26 | 114592 | 59617
2024-09-02 | 126334 | 34082
2024-09-09 | 91772 | 41285
2024-09-16 | 51646 | 63016
2024-09-23 | 138085 | 68186
2024-09-30 | 113294 | 53090
2024-10-07 | 89735 | 44562
2024-10-14 | 80457 | 40287
2024-10-21 | 118998 | 59225
2024-10-28 | 118350 | 56535
2024-11-04 | 139484 | 57013
2024-11-11 | 75414 | 62956
2024-11-18 | 102400 | 35947
2024-11-25 | 65493 | 75893
2024-12-02 | 102970 | 52381
2024-12-09 | 80717 | 54791
2024-12-16 | 147972 | 42635
2024-12-23 | 100771 | 57845
2024-12-30 | 94028 | 52851
2025-01-06 | 71491 | 49738
2025-01-13 | 118374 | 34987

## Notes & Calcs
PROJECT NOTES & CALCULATIONS
BUDGET STATUS:
Original Budget: | $650,000
Current Forecast: | $658,500
Variance: | ($8,500)
MAJOR ISSUES:
1. Kitchen cabinets over by $2,100 - client upgrade NOT invoiced
2. Electrical over by $1,240 - extra power points variation approved
3. Plumbing fixtures over by $580 - client selections
CLIENT VARIATIONS NOT INVOICED:
VO-002: Extra window | $1,200
VO-003: Bathroom tile upgrade | $2,800
VO-004: Extra waterproofing | $1,500
VO-006: 8x power points | $960
TOTAL REVENUE LEAKAGE: | $6,460