## Summary
PROJECT SUMMARY
Project Name | Project A - 123 Sunset Boulevard
Contract Value | 650000
Start Date | 2024-01-15
Estimated Completion | 2024-10-30
Percent Complete | 65%
FINANCIAL SUMMARY
Total Budget | 650000
Total Actual | 574600
Total Committed | 83900
Total Forecast | 658500
Total Variance | -8500
Over Budget Amount | 8500
Category Count | 9
Line Item Count | 72
Item 19 | 33056
Item 20 | 1458
Item 21 | 7398
Item 22 | 15921
Item 23 | 43631
Item 24 | 40609
Item 25 | 10911
Item 26 | 14441
Item 27 | 19254
Item 28 | 22457
Item 29 | 42619
Item 30 | 20773
Item 31 | 14099
Item 32 | 31402
Item 33 | 1067
Item 34 | 16288
Item 35 | 38544
Item 36 | 18964
Item 37 | 45762
Item 38 | 10637
Item 39 | 14715
Item 40 | 6622
Item 41 | 47428
Item 42 | 8400
Item 43 | 11752
Item 44 | 21199
Item 45 | 38737
Item 46 | 20832
Item 47 | 39372
Item 48 | 38818
Item 49 | 31855
Item 50 | 5666
Item 51 | 16059
Item 52 | 22999
Item 53 | 9074

## Budget Details
Category | Sub Category | Budget | Actual | Committed | Forecast | Variance | % Complete | Notes
LAND & ACQUISITION | Land Purchase - 123 Sunset Blvd | 285000 | 285000 | 0 | 285000 | 0 | 100 | PAID - Settlement 15/Jan/2024
LAND & ACQUISITION | Stamp Duty | 12750 | 12750 | 0 | 12750 | 0 | 100
LAND & ACQUISITION | Legal Fees - Conveyancing | 1850.5 | 1850.5 | 0 | 1850.5 | 0 | 100 | Jenkins & Associates
LAND & ACQUISITION | Survey & Title Search | 950 | 950 | 0 | 950 | 0 | 100
LAND & ACQUISITION | Soil Testing & Geotechnical | 2400 | 2650 | 0 | 2650 | -250 | 100 | Extra tests required - clay soil issues
DESIGN & APPROVALS | Architect - Concept Design | 8500 | 8500 | 0 | 8500 | 0 | 100 | Design Co. - PAID
DESIGN & APPROVALS | Architect - Detailed Plans | 15500 | 15500 | 0 | 15500 | 0 | 100
DESIGN & APPROVALS | Design Revisions | 2500 | 3240 | 0 | 3240 | -740 | 100 | 3 revision rounds!! client kept changing mind
DESIGN & APPROVALS | Structural Engineering | 5200 | 5200 | 0 | 5200 | 0 | 100
DESIGN & APPROVALS | Civil Engineering | 3800 | 3950 | 0 | 3950 | -150 | 100 | slight overrun
DESIGN & APPROVALS | Electrical Design & Plans | 2100 | 2100 | 0 | 2100 | 0 | 100
DESIGN & APPROVALS | Plumbing/Hydraulic Design | 1850 | 1850 | 0 | 1850 | 0 | 100
DESIGN & APPROVALS | Council DA Fees & Permits | 4250 | 4680 | 0 | 4680 | -430 | 100 | Extra fees for variation - ugh
SITE PREPARATION | Site Clearing & Demolition | 3500 | 3500 | 0 | 3500 | 0 | 100 | Old garage removed
SITE PREPARATION | Excavation & Earthworks | 8200 | 8620 | 0 | 8620 | -420 | 100 | Hit rock - extra excavation needed. check this!
SITE PREPARATION | Temp Fencing & Site Security | 1200 | 1200 | 0 | 1200 | 0 | 100
SITE PREPARATION | Temp Power & Water | 1850 | 1850 | 0 | 1850 | 0 | 100
SITE PREPARATION | Site Toilet Hire | 1800 | 1650 | 0 | 1650 | 150 | 100 | Better rate found
SITE PREPARATION | Site Shed & Storage | 950 | 950 | 0 | 950 | 0 | 100
FOUNDATION | Footings - Concrete | 12500 | 12500 | 0 | 12500 | 0 | 100
FOUNDATION | Footings - Steel Reinforcement | 3200 | 3200 | 0 | 3200 | 0 | 100
FOUNDATION | Footings - Labour | 4500 | 4500 | 0 | 4500 | 0 | 100 | BigDig Excavations
FOUNDATION | Termite Treatment/Barrier | 1800 | 1800 | 0 | 1800 | 0 | 100
FOUNDATION | Slab - Concrete Supply | 15800 | 15800 | 0 | 15800 | 0 | 100 | ReadyMix Concrete Co
FOUNDATION | Slab - Steel Mesh & Reo | 2800 | 2800 | 0 | 2800 | 0 | 100
FOUNDATION | Slab - Waterproofing | 2200 | 3090 | 0 | 3090 | -890 | 100 | Extra membrane required - wet site. URGENT fix needed
FOUNDATION | Slab - Pour & Finish Labour | 6500 | 6500 | 0 | 6500 | 0 | 100
FRAME & STRUCTURE | Timber Frame Supply | 28500 | 28500 | 0 | 28500 | 0 | 100 | Bunnings Trade
FRAME & STRUCTURE | Frame Erection - Labour | 18000 | 18000 | 0 | 18000 | 0 | 100 | FastFrame Carpentry
FRAME & STRUCTURE | Roof Trusses Supply | 12400 | 12400 | 0 | 12400 | 0 | 100 | Custom Trusses Ltd
FRAME & STRUCTURE | Roof Truss Install | 3500 | 3500 | 0 | 3500 | 0 | 100
FRAME & STRUCTURE | Engineering Inspections | 850 | 850 | 0 | 850 | 0 | 100
FRAME & STRUCTURE | Bracing & Connectors | 1950 | 1950 | 0 | 1950 | 0 | 100
FRAME & STRUCTURE | Scaffolding Hire | 4200 | 4200 | 0 | 4200 | 0 | 100 | SkyHigh Scaffolding - 8 weeks
EXTERNAL ENVELOPE | Roofing Tiles/Material | 14500 | 15150 | 0 | 15150 | -650 | 100 | Extra tiles for breakage - normal wastage
EXTERNAL ENVELOPE | Roof Installation Labour | 8500 | 8500 | 0 | 8500 | 0 | 100 | TopRoof Tilers
EXTERNAL ENVELOPE | Gutters & Downpipes | 3200 | 3200 | 0 | 3200 | 0 | 100 | Colorbond
EXTERNAL ENVELOPE | Roof Flashing & Trim | 1850 | 1850 | 0 | 1850 | 0 | 100
EXTERNAL ENVELOPE | Brickwork - Materials | 18500 | 18500 | 0 | 18500 | 0 | 100 | Austral face brick
EXTERNAL ENVELOPE | Brickwork - Labour | 24000 | 24000 | 0 | 24000 | 0 | 100 | Premier Bricklaying
EXTERNAL ENVELOPE | Windows - Supply | 12800 | 12800 | 0 | 12800 | 0 | 100 | Aluminium frame double glazed
EXTERNAL ENVELOPE | Windows - Installation | 2400 | 2400 | 0 | 2400 | 0 | 100
EXTERNAL ENVELOPE | External Doors | 3500 | 3500 | 0 | 3500 | 0 | 100 | Front door + garage
EXTERNAL ENVELOPE | External Waterproofing | 2800 | 2800 | 0 | 2800 | 0 | 100 | Balcony & wet areas
SERVICES - PLUMBING | Plumbing Rough-in | 8500 | 8500 | 0 | 8500 | 0 | 100 | John's Plumbing Services
SERVICES - PLUMBING | Plumbing Fixtures | 6800 | 7380 | 0 | 7380 | -580 | 100 | Client upgrade to better taps - NOT INVOICED TO CLIENT!!
SERVICES - PLUMBING | Hot Water System | 2400 | 2400 | 0 | 2400 | 0 | 100 | Gas instant
SERVICES - PLUMBING | Gas Line Installation | 1850 | 1850 | 0 | 1850 | 0 | 100
SERVICES - ELECTRICAL | Electrical Rough-in | 9500 | 10740 | 0 | 10740 | -1240 | 100 | Extra circuits added - outdoor kitchen etc. pending client approval???
SERVICES - ELECTRICAL | Switchboard & Meter | 2800 | 2800 | 0 | 2800 | 0 | 100 | Upgraded 3-phase
SERVICES - ELECTRICAL | Light Fixtures | 3500 | 0 | 3500 | 3500 | 0 | 0 | On order - delivery next week
SERVICES - ELECTRICAL | Power Points & Switches | 2200 | 0 | 2200 | 2200 | 0 | 0 | Install next week
SERVICES - ELECTRICAL | Data/TV Cabling | 1800 | 1800 | 0 | 1800 | 0 | 100 | Cat6 throughout
SERVICES - HVAC | Ducted AC System | 12500 | 0 | 12500 | 12500 | 0 | 0 | Install scheduled 2 weeks - AirMaster HVAC
INTERNAL FITOUT | Insulation - Ceiling & Walls | 4200 | 4200 | 0 | 4200 | 0 | 100 | R3.5 ceiling, R2.5 walls
INTERNAL FITOUT | Plasterboard Supply & Install | 18500 | 18500 | 0 | 18500 | 0 | 100 | Complete Plastering Co
INTERNAL FITOUT | Cornice | 1850 | 1850 | 0 | 1850 | 0 | 100 | 90mm plain
INTERNAL FITOUT | Internal Doors | 4800 | 0 | 4800 | 4800 | 0 | 0 | Ordered - arrival 1 week
INTERNAL FITOUT | Kitchen - Cabinets | 18000 | 0 | 20100 | 20100 | -2100 | 0 | CLIENT UPGRADE stone benchtop instead of laminate - NOT CHARGED YET!!
INTERNAL FITOUT | Kitchen - Appliances | 6500 | 0 | 6500 | 6500 | 0 | 0 | Bosch package
INTERNAL FITOUT | Bathroom Vanities | 3200 | 0 | 3200 | 3200 | 0 | 0 | x2 bathrooms + ensuite
INTERNAL FITOUT | Bathroom Tiles - Supply | 5800 | 5800 | 0 | 5800 | 0 | 100 | Floor & wall tiles purchased
INTERNAL FITOUT | Bathroom Tiles - Labour | 6500 | 0 | 6500 | 6500 | 0 | 30 | In progress - PremierTile
INTERNAL FITOUT | Flooring - Timber | 12500 | 0 | 12500 | 12500 | 0 | 0 | Engineered oak - delivery pending
INTERNAL FITOUT | Flooring - Carpet | 3800 | 0 | 3800 | 3800 | 0 | 0 | Bedrooms - not ordered yet
INTERNAL FITOUT | Painting - Prep & Paint | 14500 | 0 | 0 | 14500 | 0 | 0 | Starts in 3 weeks - ColorPro
EXTERNAL WORKS | Driveway - Concrete | 4800 | 0 | 0 | 4800 | 0 | 0 | Not started
EXTERNAL WORKS | Paths & Paving | 3200 | 0 | 0 | 3200 | 0 | 0
EXTERNAL WORKS | Fencing | 5500 | 0 | 0 | 5500 | 0 | 0 | Colorbond - quote pending
EXTERNAL WORKS | Landscaping & Gardens | 6800 | 0 | 0 | 6800 | 0 | 0 | Final stage
EXTERNAL WORKS | Deck/Alfresco | 8500 | 0 | 0 | 8500 | 0 | 0 | Timber deck - not started
EXTERNAL WORKS | External Lighting | 1200 | 0 | 0 | 1200 | 0 | 0
PROFESSIONAL SERVICES | Quantity Surveyor | 1500 | 1500 | 0 | 1500 | 0 | 100
PROFESSIONAL SERVICES | Building Certifier | 3200 | 2100 | 1100 | 3200 | 0 | 65 | Stage payments
PROFESSIONAL SERVICES | Surveyor - Set Out | 850 | 850 | 0 | 850 | 0 | 100
PROFESSIONAL SERVICES | Site Inspections | 1200 | 780 | 420 | 1200 | 0 | 65 | Ongoing

## Category Summary
CATEGORY SUMMARY
Category | Budget | Actual | Committed | Forecast | Variance
LAND & ACQUISITION | 302950.5 | 303200.5 | 0 | 303200.5 | -250
DESIGN & APPROVALS | 43700 | 45020 | 0 | 45020 | -1320
SITE PREPARATION | 17500 | 17770 | 0 | 17770 | -270
FOUNDATION | 49300 | 50190 | 0 | 50190 | -890
FRAME & STRUCTURE | 69400 | 69400 | 0 | 69400 | 0
EXTERNAL ENVELOPE | 92050 | 92700 | 0 | 92700 | -650
SERVICES - PLUMBING | 19550 | 20130 | 0 | 20130 | -580
SERVICES - ELECTRICAL | 19800 | 15340 | 5700 | 21040 | -1240
SERVICES - HVAC | 12500 | 0 | 12500 | 12500 | 0
INTERNAL FITOUT | 100150 | 30350 | 57400 | 102250 | -2100
EXTERNAL WORKS | 30000 | 0 | 0 | 30000 | 0
PROFESSIONAL SERVICES | 6750 | 5230 | 1520 | 6750 | 0