## Budget Summary
SUNSET BOULEVARD PROJECT - MASTER BUDGET
Project: 123 Sunset Boulevard, Sydney NSW 2000
Budget Date: 21 October 2025
Cost Category | Budget Amount | Actual Spent | Variance | % Spent | Status | Notes
Land & Acquisition | 266480 | 266480 |  |  | Complete | All settlement costs paid
Design & Engineering | 28500 | 24850 |  |  | Complete | Final invoices received
Council Permits & Approvals | 8950 | 8950 |  |  | Complete | All permits approved
Site Establishment | 12400 | 11280 |  |  | In Progress | Scaffolding ongoing
Foundation & Slab | 45200 | 42850 |  |  | Complete | Slab poured and cured
Frame & Structure | 85600 | 78200 |  |  | In Progress | Roof trusses installed
Windows & External Doors | 24800 | 24800 |  |  | Complete | All units installed
Roofing & Gutters | 18200 | 16500 |  |  | In Progress | 80% complete
External Cladding | 32400 | 15200 |  |  | In Progress | Brickwork underway
Plumbing (Rough-in) | 22800 | 18400 |  |  | In Progress | First fix complete
Electrical (Rough-in) | 28600 | 22100 |  |  | In Progress | First fix underway
Insulation & Sarking | 8900 | 0 |  |  | Not Started | Scheduled next month
Plasterboard & Lining | 24500 | 0 |  |  | Not Started | Post electrical rough-in
Tiling (Bathrooms & Kitchen) | 18400 | 0 |  |  | Not Started | Awaiting plastering
Kitchen & Cabinetry | 38500 | 19250 |  |  | In Progress | 50% deposit paid
Bathroom Fit-out | 16200 | 0 |  |  | Not Started | Materials ordered
Flooring | 19800 | 0 |  |  | Not Started | Timber on order
Painting (Internal & External) | 22600 | 0 |  |  | Not Started | Scheduled month 8
Final Electrical (Fit-off) | 12400 | 0 |  |  | Not Started | Post painting
Final Plumbing (Fit-off) | 10200 | 0 |  |  | Not Started | Post tiling
Landscaping & Driveway | 28400 | 0 |  |  | Not Started | Final stage
Contingency (5%) | 32500 | 8450 |  |  | Partial | Variation orders
TOTAL PROJECT BUDGET

## Cash Flow Forecast
PROJECT CASH FLOW FORECAST
Month | Planned Spend | Actual Spend | Variance | Cumulative Spent
June 2024 | 266000 | 266480
July 2024 | 35000 | 33850
August 2024 | 58000 | 55120
September 2024 | 72000 | 68200
October 2024 | 48000 | 45850
November 2024 | 45000 | 0
December 2024 | 38000 | 0
January 2025 | 28000 | 0
February 2025 | 24000 | 0
March 2025 | 36000 | 0