## Permit Tracking
Permit Type | Authority | Application Date | Approval Date | Permit Number | Fee (Ex GST) | GST | Total Fee | Status | Expiry Date
Development Application | City of Sydney Council | 2024-03-15 | 2024-05-20 | DA-2024-1234 | 8500 | 850 | 9350 | APPROVED | 2025-05-20
Construction Certificate | Private Certifier - BuildCert | 2024-05-25 | 2024-06-10 | CC-2024-5678 | 3200 | 320 | 3520 | APPROVED | 2025-06-10
Demolition Permit | City of Sydney Council | 2024-06-01 | 2024-06-05 | DEM-2024-0912 | 850 | 85 | 935 | APPROVED | 2024-12-05
Road Opening Permit | Sydney Water | 2024-06-15 | 2024-06-20 | ROP-2024-3456 | 1200 | 120 | 1320 | APPROVED | 2024-09-20
Hoarding Permit | City of Sydney Council | 2024-06-10 | 2024-06-18 | HP-2024-7890 | 650 | 65 | 715 | APPROVED | 2024-12-18
Asbestos Removal License | SafeWork NSW | 2024-05-15 | 2024-05-22 | ARL-2024-1122 | 1100 | 110 | 1210 | APPROVED | 2027-05-22
Crane Permit | City of Sydney Council | 2024-07-01 | 2024-07-05 | CP-2024-3344 | 2400 | 240 | 2640 | APPROVED | 2024-11-05
Occupation Certificate | Private Certifier - BuildCert | 2024-09-15 | PENDING | OC-2024-PEND | 2800 | 280 | 3080 | IN PROGRESS | TBD
TOTAL FEES: