## Payment Schedule
Subcontractor | Trade | Invoice Number | Invoice Date | Description | Amount (Ex GST) | GST | Total | Due Date | Payment Date | Status
Metro Demolition | Demolition | MD-2024-001 | 2024-07-05 | Full demolition complete | 13636.36 | 1363.64 | 15000 | 2024-07-19 | 2024-07-18 | PAID
BetaMix Concrete | Concrete | BM-2024-078 | 2024-07-25 | Slab pour - 45m³ | 36818.18 | 3681.82 | 40500 | 2024-08-08 | 2024-08-05 | PAID
BetaMix Concrete | Concrete | BM-2024-089 | 2024-08-05 | Additional concrete 12m³ | 4090.91 | 409.09 | 4500 | 2024-08-19 | 2024-08-20 | PAID
Timberland Frames | Framing | TF-2024-156 | 2024-08-25 | Framing complete | 60000 | 6000 | 66000 | 2024-09-08 | 2024-09-05 | PAID
Metro Roofing | Roofing | MR-2024-034 | 2024-09-10 | 50% progress payment | 12954.55 | 1295.45 | 14250 | 2024-09-24 | PENDING | INVOICED
ProPlumb Services | Plumbing | PP-2024-189 | 2024-09-15 | Rough-in complete | 15909.09 | 1590.91 | 17500 | 2024-09-29 | PENDING | INVOICED
Spark Electrical | Electrical | SE-2024-267 | 2024-09-18 | First fix electrical | 14545.45 | 1454.55 | 16000 | 2024-10-02 | PENDING | INVOICED
TOTAL PAYMENTS: