## Daily Site Report
DAILY SITE REPORT - July 25, 2024
Project: 123 Sunset Blvd ¦ Supervisor: Robert Chen
Weather Conditions: | Sunny, 18°C, Light winds
Trades On Site: | Framers (4), Labourers (2), Crane Operator (1)
WORK COMPLETED TODAY
Task | Progress | Workers | Notes
Timber frame - South wall | 100% | 2 | Complete and braced
Timber frame - North wall | 75% | 2 | To finish tomorrow
LVL beam installation | 100% | 2 | All beams installed
Material delivery | 100% | 1 | Roof trusses delivered
ISSUES / DELAYS:
- None reported
PLANNED FOR TOMORROW:
- Complete north wall framing
- Install roof trusses (crane scheduled)