## Safety Inspections
SITE SAFETY INSPECTION LOG
Inspection Date | Inspector | Area Inspected | Issues Found | Corrective Action | Status
2024-07-01 | SafeWork NSW | Scaffolding Setup | None | N/A | PASSED
2024-07-15 | R. Chen | Site Perimeter Fencing | Gap in fence near gate | Repaired same day | CLOSED
2024-07-22 | R. Chen | Electrical Cords & Tools | Damaged extension cord | Cord replaced | CLOSED
2024-08-05 | R. Chen | Fall Protection | None | N/A | PASSED
2024-08-12 | SafeWork NSW | General Site Inspection | None | N/A | PASSED
2024-08-19 | R. Chen | Ladder Safety | Ladder not tagged | Tag applied | CLOSED
2024-08-26 | R. Chen | PPE Compliance | All workers compliant | N/A | PASSED