## Week 31 Summary
WEEKLY SITE REPORT - WEEK 31 (July 29 - Aug 4, 2024)
Overall Progress: 62% Complete
Milestone | Planned % | Actual % | Variance | Status
Demolition | 100 | 100 | 0 | COMPLETE
Foundation & Slab | 100 | 100 | 0 | COMPLETE
Framing | 80 | 85 | 5 | AHEAD
Roofing | 40 | 35 | -5 | SLIGHTLY BEHIND
Rough-in Plumbing | 30 | 25 | -5 | SLIGHTLY BEHIND
Rough-in Electrical | 20 | 15 | -5 | SLIGHTLY BEHIND
KEY ACHIEVEMENTS:
- Timber framing 85% complete (ahead of schedule)
- All structural beams installed
- Roof trusses delivered
ISSUES:
- Plumbing materials delayed 3 days (supplier issue)