## Change Orders
CHANGE ORDER LOG - 123 Sunset Blvd Project
CO Number | Related VO | Description | Original Cost | Revised Cost | Difference | Status
CO-001 | VO-001 | Kitchen benchtop stone upgrade | 1850 | 5050 | 3200 | INVOICED
CO-002 | VO-002 | Skylight installation | 0 | 4500 | 4500 | INVOICED
CO-003 | VO-003 | Additional power points | 0 | 850 | 850 | INVOICED
CO-004 | VO-004 | Timber flooring upgrade | 4200 | 12700 | 8500 | APPROVED
CO-005 | VO-005 | Extra exhaust fan | 0 | 650 | 650 | APPROVED
TOTAL CHANGE ORDERS: