## Variation Orders
VO Number | Date Raised | Description | Requested By | Cost Impact | Time Impact (days) | Status | Approval Date | Notes
VO-001 | 2024-07-10 | Upgrade kitchen benchtop to stone | Client | 3200 | 0 | APPROVED | 2024-07-12 | Change from laminate
VO-002 | 2024-07-18 | Add skylights in living area (2 units) | Architect | 4500 | 2 | APPROVED | 2024-07-20 | Design enhancement
VO-003 | 2024-08-05 | Additional power points in bedrooms (6 units) | Client | 850 | 0 | APPROVED | 2024-08-06 | Client request
VO-004 | 2024-08-15 | Change from carpet to timber flooring | Client | 8500 | 3 | APPROVED | 2024-08-17 | Upgrade to engineered oak
VO-005 | 2024-08-22 | Extra bathroom exhaust fan | Building Inspector | 650 | 0 | APPROVED | 2024-08-22 | Compliance requirement
VO-006 | 2024-09-01 | Upgrade to designer light fixtures | Client | 2800 | 0 | PENDING | - | Quote provided
TOTAL VARIATIONS: