## Progress Claim 01
PROGRESS CLAIM #01 - JULY 2024
Project: 123 Sunset Blvd ¦ Client: Smith Family Trust
Claim Period: June 15 - July 31, 2024
Work Package | Contract Value | Claimed to Date | % Complete | This Claim
Site Establishment | 8000 | 8000 | 100 | 8000
Demolition | 15000 | 15000 | 100 | 15000
Foundation Works | 45000 | 45000 | 100 | 45000
Slab | 38000 | 38000 | 100 | 38000
Framing | 66000 | 19800 | 30 | 19800
Preliminaries | 25000 | 7500 | 30 | 7500
SUBTOTAL:
GST (10%):
CLAIM TOTAL: