## Budget Summary
MASTER PROJECT BUDGET - Project B - 456 Ocean Drive
PRELIMINARIES | Site Establishment | 25000 | 22500 | 2500 | 25000 | 0 | 90
PRELIMINARIES | Project Management Fees | 45000 | 37500 | 7500 | 45000 | 0 | 83
PRELIMINARIES | Insurance & Permits | 15000 | 16500 | 0 | 16500 | -1500 | 100 | Council fees higher than expected
DEMOLITION & SITE PREP | Interior Demolition | 35000 | 38500 | 0 | 38500 | -3500 | 100 | Asbestos found - extra cost
DEMOLITION & SITE PREP | Floor Grinding & Prep | 10000 | 9500 | 0 | 9500 | 500 | 100
PARTITIONS & CEILINGS | Steel Stud Framing | 75000 | 60000 | 15000 | 75000 | 0 | 80
PARTITIONS & CEILINGS | Plasterboard & Insulation | 85000 | 70000 | 15000 | 85000 | 0 | 82 | check invoice #INV-DS-998
PARTITIONS & CEILINGS | Suspended Ceilings | 20000 | 18500 | 1500 | 20000 | 0 | 93
FLOORING | Carpet Tiles - Office Area | 45000 | 0 | 45000 | 45000 | 0 | 0 | Deposit paid
FLOORING | Vinyl - Breakout Area | 25000 | 5000 | 20000 | 25000 | 0 | 20
FLOORING | Epoxy - Server Room | 15000 | 0 | 15000 | 15000 | 0 | 0
FLOORING | Polished Concrete - Reception | 10000 | 10000 | 0 | 10000 | 0 | 100 | Complete
JOINERY | Reception Desk | 18000 | 5000 | 13000 | 18000 | 0 | 28
JOINERY | Kitchen & Breakout Cabinets | 45000 | 10000 | 35000 | 45000 | 0 | 22
JOINERY | Meeting Room Credenzas | 32000 | 0 | 32000 | 32000 | 0 | 0
JOINERY | Custom Wall Paneling | 65000 | 0 | 65000 | 65000 | 0 | 0 | Long lead time item
JOINERY | Storage Units | #REF! | 15000 | 45000 | 60000 |  | 25 | Budget ???
MECHANICAL (HVAC) | AC Units & Ducting | 90000 | 40000 | 50000 | 95000 | -5000 | 44 | URGENT - Variation approved
MECHANICAL (HVAC) | Exhaust Fans | 25000 | 10000 | 15000 | 25000 | 0 | 40
MECHANICAL (HVAC) | BMS & Controls | 35000 | 10000 | 25000 | 35000 | 0 | 29
ELECTRICAL & DATA | Main Switchboard Upgrade | 40000 | 42500 | 0 | 42500 | -2500 | 100
ELECTRICAL & DATA | Lighting & Controls | 85000 | 30000 | 55000 | 90000 | -5000 | 35 | Smart lighting VO approved
ELECTRICAL & DATA | Power Outlets | 65000 | 25000 | 40000 | 65000 | 0 | 38
ELECTRICAL & DATA | Data Cabling & Comms Rack | 60000 | 20000 | 40000 | 60000 | 0 | 33
HYDRAULICS (PLUMBING) | Pipework Rough-in | 35000 | 28000 | 7000 | 35000 | 0 | 80
HYDRAULICS (PLUMBING) | Fixtures & Fit-off | 40000 | 0 | 40000 | 40000 | 0 | 0
FIRE SERVICES | Sprinkler System | 40000 | 10000 | 30000 | 42000 | -2000 | 25 | Compliance issue found
FIRE SERVICES | Smoke Detectors & Panel | 20000 | 8000 | 12000 | 20000 | 0 | 40
FINISHES | Painting | 55000 | 0 | 55000 | 55000 | 0 | 0
FINISHES | Glazing & Film | 35000 | 0 | 35000 | 35000 | 0 | 0
Hidden rows 10-12

## Detailed Costs
Date | Supplier | Invoice# | PO# | Description | Category | Amount | GST | Total | Paid? | Payment Date
06/09/2024 | Miami Demo Group | INV-4154 | PO-871 |  | FINISHES | 3794.2708 | 379.4271 | 4173.6979 | No | 11/10/2024
2024/10/04 | Hydro Plumbers | INV-9099 | PO-243 |  | MECHANICAL | 3792.6311 | 379.2631 | 4171.8943 | Yes | 21/10/2024
2024/08/30 | ACME Mechanical | INV-6390 | PO-792 |  | DEMOLITION | 1412.0738 | 141.2074 | 1553.2812 | No
10/09/2024 |  | INV-9218 | PO-262 |  | DEMOLITION | 4720.8718 | 472.0872 | 5192.9589 | No | 26/08/2024
06/08/2024 | ACME Mechanical | INV-6916 | PO-819 |  | FIRE | 3263.1934 | 326.3193 | 3589.5127 | No | 12/09/2024
12/08/2024 | Miami Demo Group | INV-4497 | PO-845 |  | MECHANICAL | 4872.04 | 487.204 | 5359.244 | No
25/09/2024 | Drywall Solutions Inc. | INV-9701 | PO-579 |  | ELECTRICAL | 2010.6778 | 201.0678 | 2211.7455 | PARTIAL | 28/09/2024
07/08/2024 | Miami Demo Group | INV-3482 | PO-294 |  | HYDRAULICS | 2683.5878 | 268.3588 | 2951.9465 | Yes | 22/08/2024
2024/09/26 | Coastal Flooring | INV-9748 | PO-406 |  | PARTITIONS | 1321.8354 | 132.1835 | 1454.0189 | Yes | 06/08/2024
08-06-24 | FireSafe Systems | INV-4741 | PO-664 |  | FIRE | 2587.2683 | 258.7268 | 2845.9952 | No
2024/10/09 | Pro Painters | INV-7169 | PO-468 |  | FINISHES | 1664.7728 | 166.4773 | 1831.25 | PARTIAL | 25/10/2024
10-15-24 | Spark Electrical | INV-9480 | PO-261 |  | ELECTRICAL | 4550.5886 | 455.0589 | 5005.6474 | PARTIAL
2024/08/17 | Hydro Plumbers | INV-9394 | PO-257 |  | PRELIMINARIES | 1965.0857 | 196.5086 | 2161.5943 | Yes
10-05-24 | Pro Painters | INV-1735 | PO-356 |  | DEMOLITION | 1259.4531 | 125.9453 | 1385.3984 | No | 09/10/2024
2024/07/25 | Coastal Flooring | INV-2775 | PO-419 |  | JOINERY | 1907.4893 | 190.7489 | 2098.2382 | No | 10/10/2024
18/09/2024 |  | INV-3612 | PO-854 |  | HYDRAULICS | 4404.2941 | 440.4294 | 4844.7235 | PARTIAL
24/07/2024 | Coastal Flooring | INV-4476 | PO-229 |  | FLOORING | 4990.5138 | 499.0514 | 5489.5651 | Yes | 12/10/2024
07-28-24 |  | INV-3811 | PO-655 |  | PRELIMINARIES | 1571.6682 | 157.1668 | 1728.835 | PARTIAL | 05/08/2024
2024/09/23 | Drywall Solutions Inc. | INV-3342 | PO-747 |  | JOINERY | 2289.3686 | 228.9369 | 2518.3055 | No
2024/07/22 | Coastal Flooring | INV-9236 | PO-728 |  | MECHANICAL | 4347.5728 | 434.7573 | 4782.3301 | Yes
08-14-24 | Drywall Solutions Inc. | INV-6008 | PO-460 |  | PRELIMINARIES | 3486.2474 | 348.6247 | 3834.8721 | Yes | 17/08/2024
08-03-24 | Hydro Plumbers | INV-7726 | PO-265 |  | MECHANICAL | 2707.5238 | 270.7524 | 2978.2761 | PARTIAL | 19/08/2024
25/08/2024 | Millwork Masters | INV-1375 | PO-480 |  | ELECTRICAL | 888.9178 | 88.8918 | 977.8096 | Yes | 09/09/2024
07-24-24 | Miami Demo Group | INV-5076 | PO-955 |  | PRELIMINARIES | 3613.6355 | 361.3636 | 3974.9991 | PARTIAL | 18/10/2024
09-21-24 | Hydro Plumbers | INV-4872 | PO-950 |  | PARTITIONS | 4170.5044 | 417.0504 | 4587.5548 | No | 27/08/2024
21/09/2024 | Glass & Glazing Co. | INV-7615 | PO-556 |  | PARTITIONS | 3332.089 | 333.2089 | 3665.2979 | Yes | 20/08/2024
21/09/2024 |  | INV-6545 | PO-692 |  | ELECTRICAL | 4577.1673 | 457.7167 | 5034.8841 | No | 19/10/2024
10-15-24 | Spark Electrical | INV-3756 | PO-923 |  | PRELIMINARIES | 2677.5062 | 267.7506 | 2945.2568 | No
07/10/2024 |  | INV-6772 | PO-476 |  | FIRE | 3089.8971 | 308.9897 | 3398.8868 | No | 12/09/2024
2024/08/25 | Glass & Glazing Co. | INV-5762 | PO-658 |  | ELECTRICAL | 4247.7419 | 424.7742 | 4672.5161 | Yes | 18/10/2024
22/09/2024 | Miami Demo Group | INV-2725 | PO-120 |  | JOINERY | 790.6151 | 79.0615 | 869.6766 | Yes | 22/08/2024
2024/10/04 | Pro Painters | INV-8645 | PO-525 |  | FLOORING | 2202.0755 | 220.2075 | 2422.283 | PARTIAL | 06/10/2024
2024/09/11 | Coastal Flooring | INV-1970 | PO-224 |  | DEMOLITION | 1784.0099 | 178.401 | 1962.4108 | No
07/08/2024 | Pro Painters | INV-5834 | PO-573 |  | MECHANICAL | 2178.9993 | 217.8999 | 2396.8992 | No | 08/09/2024
08-07-24 | Miami Demo Group | INV-4115 | PO-768 |  | FINISHES | 4145.0501 | 414.505 | 4559.5551 | Yes | 02/10/2024
28/09/2024 | Coastal Flooring | INV-4382 | PO-501 |  | DEMOLITION | 2856.9351 | 285.6935 | 3142.6286 | No
2024/08/09 | Glass & Glazing Co. | INV-9492 | PO-756 |  | JOINERY | 2830.5404 | 283.054 | 3113.5944 | PARTIAL | 11/10/2024
08-04-24 | Pro Painters | INV-5395 | PO-208 |  | PARTITIONS | 593.1944 | 59.3194 | 652.5138 | PARTIAL
21/08/2024 | Coastal Flooring | INV-3035 | PO-430 |  | ELECTRICAL | 1010.5298 | 101.053 | 1111.5828 | Yes
2024/10/09 | Drywall Solutions Inc. | INV-1558 | PO-676 |  | PRELIMINARIES | 571.5838 | 57.1584 | 628.7422 | No | 12/09/2024
16/10/2024 | Pro Painters | INV-3863 | PO-258 |  | HYDRAULICS | 1389.0334 | 138.9033 | 1527.9367 | PARTIAL | 23/09/2024
2024/08/09 | Drywall Solutions Inc. | INV-3569 | PO-784 |  | DEMOLITION | 4165.0977 | 416.5098 | 4581.6074 | Yes | 03/10/2024
2024/09/29 | Hydro Plumbers | INV-9786 | PO-526 |  | PARTITIONS | 3939.7582 | 393.9758 | 4333.734 | No | 31/08/2024
09-28-24 | FireSafe Systems | INV-5771 | PO-546 |  | FINISHES | 1342.6415 | 134.2642 | 1476.9057 | Yes | 24/09/2024
08-29-24 | Coastal Flooring | INV-9112 | PO-501 |  | HYDRAULICS | 794.7694 | 79.4769 | 874.2463 | PARTIAL
09-22-24 | Millwork Masters | INV-1462 | PO-419 |  | FINISHES | 2908.686 | 290.8686 | 3199.5546 | Yes | 17/09/2024
20/08/2024 |  | INV-9712 | PO-834 |  | HYDRAULICS | 2203.5251 | 220.3525 | 2423.8776 | PARTIAL | 25/08/2024
2024/08/10 | Glass & Glazing Co. | INV-4562 | PO-612 |  | DEMOLITION | 4521.5232 | 452.1523 | 4973.6755 | PARTIAL | 11/09/2024
12/08/2024 | Miami Demo Group | INV-6284 | PO-171 |  | HYDRAULICS | 1700.4047 | 170.0405 | 1870.4451 | Yes | 13/08/2024
23/07/2024 | Spark Electrical | INV-2110 | PO-317 |  | PARTITIONS | 2842.7132 | 284.2713 | 3126.9845 | No
09-12-24 |  | INV-4270 | PO-442 |  | FIRE | 3889.6416 | 388.9642 | 4278.6057 | Yes | 17/10/2024
2024/09/25 |  | INV-6663 | PO-981 |  | FLOORING | 3827.0336 | 382.7034 | 4209.737 | Yes | 24/09/2024
14/09/2024 |  | INV-8371 | PO-606 |  | JOINERY | 4251.7404 | 425.174 | 4676.9144 | PARTIAL | 10/08/2024
13/10/2024 |  | INV-9498 | PO-573 |  | PARTITIONS | 1463.1252 | 146.3125 | 1609.4377 | Yes | 02/10/2024
03/10/2024 | Hydro Plumbers | INV-9261 | PO-823 |  | PARTITIONS | 4704.3341 | 470.4334 | 5174.7675 | Yes | 08/10/2024
30/07/2024 | Glass & Glazing Co. | INV-5066 | PO-552 |  | FIRE | 1828.2607 | 182.8261 | 2011.0868 | No | 14/08/2024
08-04-24 |  | INV-3827 | PO-949 |  | DEMOLITION | 4665.4237 | 466.5424 | 5131.9661 | No | 31/08/2024
08-27-24 | Drywall Solutions Inc. | INV-2185 | PO-353 |  | FIRE | 3938.4539 | 393.8454 | 4332.2993 | Yes | 28/10/2024
10-01-24 |  | INV-4501 | PO-723 |  | MECHANICAL | 1162.0478 | 116.2048 | 1278.2526 | PARTIAL
2024/09/23 | Glass & Glazing Co. | INV-9402 | PO-114 |  | DEMOLITION | 3687.1202 | 368.712 | 4055.8323 | PARTIAL | 02/10/2024
09-09-24 | Drywall Solutions Inc. | INV-9827 | PO-458 |  | JOINERY | 1509.5806 | 150.9581 | 1660.5387 | PARTIAL
17/08/2024 | Spark Electrical | INV-2447 | PO-195 |  | PARTITIONS | 4468.7197 | 446.872 | 4915.5917 | No | 20/10/2024
09-02-24 |  | INV-8897 | PO-721 |  | HYDRAULICS | 2344.6686 | 234.4669 | 2579.1355 | Yes | 07/08/2024
2024/09/29 | ACME Mechanical | INV-8899 | PO-517 |  | MECHANICAL | 621.9331 | 62.1933 | 684.1264 | PARTIAL | 17/09/2024
26/07/2024 | FireSafe Systems | INV-9951 | PO-836 |  | PRELIMINARIES | 2619.6222 | 261.9622 | 2881.5845 | PARTIAL | 07/08/2024
08-15-24 | Miami Demo Group | INV-4736 | PO-215 |  | DEMOLITION | 4381.9015 | 438.1901 | 4820.0916 | Yes | 16/10/2024
10-13-24 | ACME Mechanical | INV-2019 | PO-770 |  | JOINERY | 3407.2477 | 340.7248 | 3747.9725 | PARTIAL
2024/09/07 | ACME Mechanical | INV-2377 | PO-818 |  | FIRE | 3153.4337 | 315.3434 | 3468.7771 | No | 12/09/2024
13/09/2024 | ACME Mechanical | INV-3834 | PO-268 |  | PRELIMINARIES | 4170.6813 | 417.0681 | 4587.7494 | No | 15/08/2024
2024/09/24 | FireSafe Systems | INV-8961 | PO-199 |  | PRELIMINARIES | 1171.7561 | 117.1756 | 1288.9317 | PARTIAL | 15/08/2024
29/07/2024 | Spark Electrical | INV-9197 | PO-746 |  | PARTITIONS | 666.2725 | 66.6273 | 732.8998 | PARTIAL
07-30-24 | Glass & Glazing Co. | INV-7796 | PO-150 |  | ELECTRICAL | 2957.1301 | 295.713 | 3252.8431 | Yes
09-18-24 | Drywall Solutions Inc. | INV-7430 | PO-876 |  | PARTITIONS | 1843.4551 | 184.3455 | 2027.8006 | No | 01/09/2024
10-04-24 | Miami Demo Group | INV-9071 | PO-925 |  | HYDRAULICS | 1596.8202 | 159.682 | 1756.5022 | Yes | 04/08/2024
2024/08/26 | FireSafe Systems | INV-4693 | PO-379 |  | FLOORING | 542.7339 | 54.2734 | 597.0072 | PARTIAL
2024/09/22 | Hydro Plumbers | INV-7352 | PO-599 |  | FINISHES | 4397.4219 | 439.7422 | 4837.1641 | Yes | 20/08/2024
07-28-24 |  | INV-3044 | PO-862 |  | FINISHES | 2003.841 | 200.3841 | 2204.2251 | PARTIAL | 23/09/2024
13/08/2024 | Pro Painters | INV-5357 | PO-970 |  | PRELIMINARIES | 646.1944 | 64.6194 | 710.8139 | No | 23/09/2024
09-26-24 | Drywall Solutions Inc. | INV-4862 | PO-521 |  | FLOORING | 895.9444 | 89.5944 | 985.5389 | No
2024/10/17 | Drywall Solutions Inc. | INV-9145 | PO-435 |  | MECHANICAL | 1532.3055 | 153.2306 | 1685.5361 | PARTIAL | 29/08/2024
06/08/2024 | Hydro Plumbers | INV-6905 | PO-733 |  | PARTITIONS | 3939.4828 | 393.9483 | 4333.4311 | Yes | 05/09/2024
14/09/2024 | Pro Painters | INV-8239 | PO-622 |  | HYDRAULICS | 3782.4603 | 378.246 | 4160.7064 | No | 03/08/2024
03/09/2024 | ACME Mechanical | INV-7934 | PO-474 |  | DEMOLITION | 4104.7651 | 410.4765 | 4515.2416 | No
09-08-24 |  | INV-8258 | PO-707 |  | FIRE | 580.8924 | 58.0892 | 638.9816 | Yes | 23/10/2024
2024/09/10 | Spark Electrical | INV-4476 | PO-523 |  | MECHANICAL | 2169.9004 | 216.99 | 2386.8905 | Yes
17/09/2024 | ACME Mechanical | INV-8403 | PO-728 |  | MECHANICAL | 3117.22 | 311.722 | 3428.942 | PARTIAL
08-28-24 | ACME Mechanical | INV-4434 | PO-934 |  | PRELIMINARIES | 1097.5962 | 109.7596 | 1207.3558 | No | 31/08/2024
12/10/2024 | Miami Demo Group | INV-7249 | PO-211 |  | PRELIMINARIES | 846.2348 | 84.6235 | 930.8582 | Yes
10-13-24 |  | INV-7379 | PO-411 |  | FINISHES | 2919.3102 | 291.931 | 3211.2412 | PARTIAL | 23/09/2024
09/10/2024 | FireSafe Systems | INV-3877 | PO-771 |  | PARTITIONS | 1401.4009 | 140.1401 | 1541.541 | Yes | 21/08/2024
19/08/2024 | Hydro Plumbers | INV-6660 | PO-900 |  | HYDRAULICS | 3418.1629 | 341.8163 | 3759.9792 | Yes | 25/08/2024
31/08/2024 | Drywall Solutions Inc. | INV-9078 | PO-454 |  | FIRE | 727.7972 | 72.7797 | 800.5769 | No
09-05-24 | Glass & Glazing Co. | INV-7602 | PO-628 |  | HYDRAULICS | 2741.0869 | 274.1087 | 3015.1955 | Yes | 26/08/2024
08-12-24 | FireSafe Systems | INV-8903 | PO-920 |  | PARTITIONS | 3203.0555 | 320.3056 | 3523.3611 | Yes | 31/08/2024
09-28-24 | Miami Demo Group | INV-4986 | PO-477 |  | DEMOLITION | 4512.2498 | 451.225 | 4963.4748 | Yes | 12/09/2024
26/07/2024 | Pro Painters | INV-8033 | PO-271 |  | DEMOLITION | 1101.0553 | 110.1055 | 1211.1609 | Yes
10-03-24 | Hydro Plumbers | INV-6569 | PO-745 |  | FLOORING | 4265.1939 | 426.5194 | 4691.7133 | Yes | 26/10/2024
2024/10/15 | Coastal Flooring | INV-1462 | PO-612 |  | PARTITIONS | 2095.9162 | 209.5916 | 2305.5078 | Yes | 28/09/2024
21/08/2024 | Miami Demo Group | INV-8284 | PO-507 |  | ELECTRICAL | 2139.1992 | 213.9199 | 2353.1191 | No | 04/08/2024
13/09/2024 | Drywall Solutions Inc. | INV-6009 | PO-419 |  | PARTITIONS | 1475.1214 | 147.5121 | 1622.6335 | Yes | 01/10/2024
21/08/2024 |  | INV-8190 | PO-261 |  | FLOORING | 3936.21 | 393.621 | 4329.831 | PARTIAL | 09/08/2024
02/09/2024 | Millwork Masters | INV-5304 | PO-570 |  | HYDRAULICS | 2999.1239 | 299.9124 | 3299.0363 | No | 09/08/2024
05/09/2024 | Spark Electrical | INV-3883 | PO-330 |  | ELECTRICAL | 2063.9797 | 206.398 | 2270.3777 | Yes | 09/10/2024
2024/10/03 | Millwork Masters | INV-6780 | PO-455 |  | PARTITIONS | 1324.833 | 132.4833 | 1457.3163 | PARTIAL
10-04-24 | Hydro Plumbers | INV-2161 | PO-878 |  | MECHANICAL | 2663.139 | 266.3139 | 2929.4529 | No | 21/08/2024

## Weekly Cashflow
Week Ending | Opening Balance | Money In | Money Out | Closing Balance | Notes
2024-07-21 | 50000 | 160902 | 107304 | 103598
2024-07-28 | 103598 | 94800 | 73828 | 124570
2024-08-04 | 124570 | 57774 | 80377 | 101967
2024-08-11 | 101967 | 117064 | 139974 | 79057
2024-08-18 | 79057 | 48488 | 83552 | 43993
2024-08-25 | 43993 | 0 | 100265 | -56272
2024-09-01 | -56272 | 45843 | 42005 | -52434
2024-09-08 | -52434 | 19665 | 56445 | -89214
2024-09-15 | -89214 | 154620 | 13705 | 52701
2024-09-22 | 51701 | 42248 | 21742 | 72207
2024-09-29 | 72207 | 124847 | 144588 | 52466 | Client payment delayed
2024-10-06 | 52466 | 166618 | 44780 | 174304
2024-10-13 | 174304 | 2228 | 123714 | 52818
2024-10-20 | 52818 | 189636 | 28886 | 213568
2024-10-27 | 213568 | 50227 | 122306 | 141489
2024-11-03 | 141489 | 60532 | 250000 | -47979
2024-11-10 | -47979 | 89037 | 54359 | -13301
2024-11-17 | -13301 | 149566 | 16963 | 119302
2024-11-24 | 119302 | 46897 | 136648 | 29551
2024-12-01 | 29551 | 70141 | 29252 | 70440

## Notes & Calculations
Notes & Calculations
Old Budget v1 (DO NOT USE) | ~~Framing: $80,000~~ | ~~Joinery: $200,000~~
Concrete Calculation | Slab Area (m2) | Rate ($/m3) | Total Cost
Contingency Check | 850 | 250